## the guinness partnership - atki
The Guinness Partnership - AtkinsRéalis Coordination & Design Board
Address List (Full PAS)
Name | UPRN | City/Town | Postcode | Sharepoint | Copy Data (tech team) | PasHub Link | Project/client | Assessment System | Retrofit Assessor | RA Date | RA Status | Pre-SAP Score | Potential SAP Score | Batch | View test | Coordinator | IOE Planned Date | Coordination Status IOE/MTP | RC Comments | Damp/mould evidence | IOE Uploaded (latest) | Latest DC/IOE | Latest DC/IOE & SAP xml upload | Proposed measures | Other measures | RC Stage 1 Confirmation | Proposed PK (Osmosis) | Approved PK | Approved by | Osm. Archetype reference | Main Designer | Designer | Design feedback on RA | Design Planned Date | Design Due Date | Design Comments | Design Requested Internally | Request Date Internally | Design reference | Retrofit Design Status | Design Upload Date | Design Revision | Design Invoice Type | Design Confirmation | Planning Status | Planning Authority | Article 4 PD Rights | Planning Comments | Footpath to front | Planning - suggested approach | Thermal bridge count | Notes - Thermal bridge calculations | Installer | Actual Measures Installed | Other measures for EPR | Contractor Hand Over To Client | Post EPC Assessor | Post EPC/EPR Status | Post EPR lig | Post EPR score | TM account | TM lodging | TM Lodgement Phase 1 | Date TM phase 1 | TM lodging comments | Missing documents | RC Compliance | Measures allocated and Funding set | Ventilation checklist uploaded | Osmosis Docc 2035 signed | Osmosis Handover signed | TM Lodgement Phase 2 | Lodgement Confirmation | Date TM full Lodgement | Item ID | HubSpot ID | Creation log | PASHub Status | Check | Damp and Mould and Repairs Comments
1 Acacia Crescent | DW_00071_1 |  | CW1 4EZ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443691375 | 489493572841 | Joseph Westwood Mar 6, 2026 2:04 PM
1 Barnabas Avenue | DW_00023_1 |  | CW1 3NS |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443691151 | 488150739160 | Joseph Westwood Mar 6, 2026 2:04 PM
1 Stewart Street | DW_00214_1 |  | CW2 7RW |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443679775 | 489379949776 | Joseph Westwood Mar 6, 2026 2:04 PM
1 Victoria Avenue | DW_00012_1 |  | CW2 7SG |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443690251 | 488103438536 | Joseph Westwood Mar 6, 2026 2:05 PM
1 Weaver Road | DW_00403_1 |  | CW5 5NJ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443691244 | 489309331675 | Joseph Westwood Mar 6, 2026 2:05 PM
10 Frank Webb Avenue | DW_00019_10 |  | CW1 3NH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443684261 | 489493572840 | Joseph Westwood Mar 6, 2026 2:05 PM
10 French Lane End | DW_00564_10 |  | CW5 8AP |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443684984 | 489509765362 | Joseph Westwood Mar 6, 2026 2:05 PM
10 Peel Square | DW_00231_10 |  | CW1 3BW |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443679499 | 489493572843 | Joseph Westwood Mar 6, 2026 2:05 PM
10 Weaver Road | DW_00403_10 |  | CW5 5NJ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443685085 | 489399770331 | Joseph Westwood Mar 6, 2026 2:05 PM
105 Ford Lane | DW_00026_105 |  | CW1 3JH |  |  |  | TGP- Atkins |  | abdul.koddus@domna.homes | 2026-03-19 | Completed & Uploaded | 63 | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443684499 | 489482746058 | Joseph Westwood Mar 6, 2026 2:05 PM
109 Underwood Lane | DW_00014_109 |  | CW1 3JP |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443668065 | 489624118463 | Joseph Westwood Mar 6, 2026 2:05 PM
11 Peel Square | DW_00231_11 |  | CW1 3BW |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443705178 | 489518619835 | Joseph Westwood Mar 6, 2026 2:05 PM
11 Vicarage Road | DW_00546_11 |  | CW1 5RR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443691378 | 489329156296 | Joseph Westwood Mar 6, 2026 2:05 PM
111 Underwood Lane | DW_00014_111 |  | CW1 3JP |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443679746 | 488845191404 | Joseph Westwood Mar 6, 2026 2:05 PM
115 Underwood Lane | DW_00014_115 |  | CW1 3JP |  |  | https://pashub.net/jobs/23c9089a-23f7-419e-a5f1-bbdc7a6b8980/details | TGP- Atkins |  | abdul.koddus@domna.homes | 2026-03-17 | Completed & Uploaded | 57D | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443685130 | 489309331679 | Joseph Westwood Mar 6, 2026 2:05 PM
12 White Avenue | DW_00013_12 |  | CW2 7SH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443679894 | 489627713770 | Joseph Westwood Mar 6, 2026 2:05 PM
125 Underwood Lane | DW_00014_125 |  | CW1 3JR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443691048 | 489616921808 | Joseph Westwood Mar 6, 2026 2:05 PM
13 Hawthorne Grove | DW_00056_13 |  | CW1 4HR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443679748 | 489558863075 | Joseph Westwood Mar 6, 2026 2:05 PM
13 St Marys Road | DW_00407_13 |  | CW5 5NU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443679577 | 489618721010 | Joseph Westwood Mar 6, 2026 2:05 PM
13 Wallfields Road | DW_00408_13 |  | CW5 5NT |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443712601 | 489493572845 | Joseph Westwood Mar 6, 2026 2:05 PM
13 White Avenue | DW_00013_13 |  | CW2 7SH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443684145 | 488197937362 | Joseph Westwood Mar 6, 2026 2:04 PM
133 Lime Tree Avenue | DW_00055_133 |  | CW1 4HT |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692538 | 489615122659 | Joseph Westwood Mar 6, 2026 2:04 PM
14 Bowen Cooke Avenue | DW_00020_14 |  | CW1 3NR |  |  | https://pashub.net/jobs/587de164-fa6a-4b16-8455-4a226a43641e/details | TGP- Atkins |  | jak.wells@domna.homes | 2026-03-24 | Completed & Uploaded | [6 empty] | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11443683530 | 489591747790 | Joseph Westwood Mar 6, 2026 2:04 PM
14 Pear Tree Avenue | DW_00028_14 |  | CW1 3SH |  |  | https://pashub.net/jobs/ef18c670-abb7-45a4-8e40-0ee4c64ea015/details | TGP- Atkins | PasHub | adam.barlow@domna.homes | 2026-03-18 | Completed & Uploaded | 58 | [5 empty] | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11443700981 | 489520401630 | Joseph Westwood Mar 6, 2026 2:05 PM
14 Pyrus Avenue | DW_00069_14 |  | CW1 4EY |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443702684 | 489613324482 | Joseph Westwood Mar 6, 2026 2:05 PM
15 Ash Road | DW_00058_15 |  | CW1 4DU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683933 | 489548245186 | Joseph Westwood Mar 6, 2026 2:05 PM
15 Bowen Cooke Avenue | DW_00020_15 |  | CW1 3NR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689484 | 489329156301 | Joseph Westwood Mar 6, 2026 2:05 PM
15 Davenham Crescent | DW_00009_15 |  | CW2 7RZ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689701 | 488421613770 | Joseph Westwood Mar 6, 2026 2:05 PM
15 Frank Webb Avenue | DW_00019_15 |  | CW1 3NH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689174 | 489627713772 | Joseph Westwood Mar 6, 2026 2:05 PM
15 Malbank | DW_00405_15 |  | CW5 5LU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689303 | 489329156299 | Joseph Westwood Mar 6, 2026 2:05 PM
15 Stewart Street | DW_00214_15 |  | CW2 7RW |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692805 | 489591747791 | Joseph Westwood Mar 6, 2026 2:05 PM
15 Vicarage Road | DW_00546_15 |  | CW1 5RR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443693479 | 489399770328 | Joseph Westwood Mar 6, 2026 2:05 PM
15 Weaver Road | DW_00403_15 |  | CW5 5NJ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443703219 | 489542931702 | Joseph Westwood Mar 6, 2026 2:05 PM
16 Barnabas Avenue | DW_00023_16 |  | CW1 3NS |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443700471 | 489611525367 | Joseph Westwood Mar 6, 2026 2:05 PM
16 Bowen Cooke Avenue | DW_00020_16 |  | CW1 3NR |  |  | https://pashub.net/jobs/13a51efd-d338-4874-9fd5-1d566a797b11/details | TGP- Atkins |  | jak.wells@domna.homes | 2026-03-23 | Completed & Uploaded | [6 empty] | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11443692829 | 489548245189 | Joseph Westwood Mar 6, 2026 2:05 PM
16 Frank Webb Avenue | DW_00019_16 |  | CW1 3NH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443694026 | 489493572839 | Joseph Westwood Mar 6, 2026 2:05 PM
16 Malbank | DW_00405_16 |  | CW5 5LU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689868 | 489606134989 | Joseph Westwood Mar 6, 2026 2:05 PM
16 Vicarage Road | DW_00546_16 |  | CW1 5RR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683875 | 489624118464 | Joseph Westwood Mar 6, 2026 2:05 PM
16 White Avenue | DW_00013_16 |  | CW2 7SH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692760 | 489518618872 | Joseph Westwood Mar 6, 2026 2:05 PM
162 Broughton Road | DW_00188_162 |  | CW1 4NR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689978 | 489558863077 | Joseph Westwood Mar 6, 2026 2:05 PM
167 Lime Tree Avenue | DW_00055_167 |  | CW1 4HY |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443694874 | 489509765363 | Joseph Westwood Mar 6, 2026 2:04 PM
17 Bowen Cooke Avenue | DW_00020_17 |  | CW1 3NR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443687038 | 489468434636 | Joseph Westwood Mar 6, 2026 2:04 PM
17 Goulden Street | DW_00029_17 |  | CW1 3LB |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443695286 | 489518619834 | Joseph Westwood Mar 6, 2026 2:04 PM
17 Pear Tree Avenue | DW_00028_17 |  | CW1 3SH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443695199 | 489588149452 | Joseph Westwood Mar 6, 2026 2:05 PM
17 Prince Edward Street | DW_00402_17 |  | CW5 5NR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443694549 | 489644164288 | Joseph Westwood Mar 6, 2026 2:05 PM
17 Vicarage Road | DW_00546_17 |  | CW1 5RR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443686737 | 489309331676 | Joseph Westwood Mar 6, 2026 2:05 PM
17 Victoria Avenue | DW_00012_17 |  | CW2 7SG |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443694550 | 489618721012 | Joseph Westwood Mar 6, 2026 2:05 PM
17 Weaver Road | DW_00403_17 |  | CW5 5NP |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443694493 | 489525670126 | Joseph Westwood Mar 6, 2026 2:05 PM
18 Barnabas Avenue | DW_00023_18 |  | CW1 3NS |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443681381 | 489509765360 | Joseph Westwood Mar 6, 2026 2:05 PM
18 Kettell Avenue | DW_00024_18 |  | CW1 3NJ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443676169 | 489520401629 | Joseph Westwood Mar 6, 2026 2:05 PM
18 Prince Edward Street | DW_00402_18 |  | CW5 5NR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443681388 | 489609730254 | Joseph Westwood Mar 6, 2026 2:05 PM
18 Queen Street | DW_00529_18 |  | CW6 9QY |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443694671 | 489566047467 | Joseph Westwood Mar 6, 2026 2:05 PM
188 Gresty Road | DW_00001_188 |  | CW2 6EJ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443681382 | 489569618106 | Joseph Westwood Mar 6, 2026 2:05 PM
19 Vauxhall Road | DW_00406_19 |  | CW5 5QR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443694672 | 488150739161 | Joseph Westwood Mar 6, 2026 2:05 PM
19 Vicarage Road | DW_00546_19 |  | CW1 5RR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443695289 | 489588149453 | Joseph Westwood Mar 6, 2026 2:05 PM
19 Victoria Avenue | DW_00012_19 |  | CW2 7SG |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443681191 | 489569617144 | Joseph Westwood Mar 6, 2026 2:05 PM
19 Wallfields Road | DW_00408_19 |  | CW5 5NT |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443694990 | 489170464999 | Joseph Westwood Mar 6, 2026 2:05 PM
19 White Avenue | DW_00013_19 |  | CW2 7SH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443675856 | 489558863076 | Joseph Westwood Mar 6, 2026 2:05 PM
2 Bowen Cooke Avenue | DW_00020_2 |  | CW1 3NR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443681532 | 489329156300 | Joseph Westwood Mar 6, 2026 2:05 PM
2 Cartwright Road | DW_00545_2 |  | CW1 5RP |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443681863 | 489332752627 | Joseph Westwood Mar 6, 2026 2:05 PM
2 Crowton Cottages | DW_00536_2 |  | CW7 4DP |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683661 | 489588149456 | Joseph Westwood Mar 6, 2026 2:04 PM
2 Fletcher Street | DW_00230_2 |  | CW1 3EE |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443688982 | 488421613771 | Joseph Westwood Mar 6, 2026 2:04 PM
2 Kettell Avenue | DW_00024_2 |  | CW1 3NJ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683523 | 489566047466 | Joseph Westwood Mar 6, 2026 2:04 PM
2 St Marys Road | DW_00407_2 |  | CW5 5NU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683679 | 488197937364 | Joseph Westwood Mar 6, 2026 2:05 PM
2 Vauxhall Road | DW_00406_2 |  | CW5 5QR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692850 | 488845191407 | Joseph Westwood Mar 6, 2026 2:05 PM
20 Bowen Cooke Avenue | DW_00020_20 |  | CW1 3NR |  |  |  | TGP- Atkins |  | abdul.koddus@domna.homes | 2026-03-19 | Completed & Uploaded | 60 | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692954 | 489606134988 | Joseph Westwood Mar 6, 2026 2:05 PM
20 Church Row | DW_00527_20 |  | CW6 9PL |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443700938 | 489170464998 | Joseph Westwood Mar 6, 2026 2:05 PM
20 Goulden Street | DW_00029_20 |  | CW1 3LA |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689441 | 489500760291 | Joseph Westwood Mar 6, 2026 2:05 PM
20 Lime Tree Avenue | DW_00055_20 |  | CW1 4HN |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443703217 | 489309331677 | Joseph Westwood Mar 6, 2026 2:05 PM
20 Malbank | DW_00405_20 |  | CW5 5LU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692357 | 489506116844 | Joseph Westwood Mar 6, 2026 2:05 PM
20 Peel Square | DW_00231_20 |  | CW1 3BW |  |  |  | TGP- Atkins |  | abdul.koddus@domna.homes | 2026-03-18 | Completed & Uploaded | 67 | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689305 | 489282400465 | Joseph Westwood Mar 6, 2026 2:05 PM
20 Weaver Road | DW_00403_20 |  | CW5 5NJ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692957 | 489624118465 | Joseph Westwood Mar 6, 2026 2:05 PM
203 Crewe Road | DW_00547_203 |  | CW1 5RU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692806 | 489482746057 | Joseph Westwood Mar 6, 2026 2:05 PM
209 Crewe Road | DW_00547_209 |  | CW1 5RU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683573 | 489618721006 | Joseph Westwood Mar 6, 2026 2:05 PM
21 Davenham Crescent | DW_00009_21 |  | CW2 7RZ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689797 | 489625915619 | Joseph Westwood Mar 6, 2026 2:05 PM
21 Frank Webb Avenue | DW_00019_21 |  | CW1 3NH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689597 | 489627713769 | Joseph Westwood Mar 6, 2026 2:05 PM
21 Weaver Road | DW_00403_21 |  | CW5 5NP |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689800 | 489624118462 | Joseph Westwood Mar 6, 2026 2:05 PM
22 Bowen Cooke Avenue | DW_00020_22 |  | CW1 3NR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692914 | 489624118461 | Joseph Westwood Mar 6, 2026 2:05 PM
22 Davenham Crescent | DW_00009_22 |  | CW2 7RZ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443700339 | 489511535829 | Joseph Westwood Mar 6, 2026 2:05 PM
22 Goulden Street | DW_00029_22 |  | CW1 3LA |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689569 | 489482746059 | Joseph Westwood Mar 6, 2026 2:05 PM
22 Kettell Avenue | DW_00024_22 |  | CW1 3NJ |  |  |  | TGP- Atkins |  | adam.barlow@domna.homes | 2026-03-16 | Completed & Uploaded | 57D | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692839 | 488421613772 | Joseph Westwood Mar 6, 2026 2:04 PM
22 Queen Street | DW_00529_22 |  | CW6 9QY |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692938 | 489566047465 | Joseph Westwood Mar 6, 2026 2:04 PM
23 Barnabas Avenue | DW_00023_23 |  | CW1 3NS |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689230 | 489500760293 | Joseph Westwood Mar 6, 2026 2:04 PM
23 Davenham Crescent | DW_00009_23 |  | CW2 7RZ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683663 | 488447249618 | Joseph Westwood Mar 6, 2026 2:05 PM
23 Frank Webb Avenue | DW_00019_23 |  | CW1 3NH |  |  | https://pashub.net/jobs/0cd52109-7cff-420a-94e5-b64859eec816/details | TGP- Atkins | PasHub | adam.barlow@domna.homes | 2026-03-16 | Completed & Uploaded | E53 | [5 empty] | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11443702666 | 488421613773 | Joseph Westwood Mar 6, 2026 2:05 PM
23 Lord Street | DW_00204_23 |  | CW2 7DH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443703214 | 489468434639 | Joseph Westwood Mar 6, 2026 2:05 PM
23 St Marys Road | DW_00407_23 |  | CW5 5NU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689702 | 489520401631 | Joseph Westwood Mar 6, 2026 2:05 PM
24 Sandfield Avenue | DW_00571_24 |  | CW5 8EU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443703216 | 489618721014 | Joseph Westwood Mar 6, 2026 2:05 PM
24 Victoria Avenue | DW_00012_24 |  | CW2 7SQ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443693136 | 489609730255 | Joseph Westwood Mar 6, 2026 2:05 PM
24 Weaver Road | DW_00403_24 |  | CW5 5NP |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443684149 | 489618721009 | Joseph Westwood Mar 6, 2026 2:05 PM
264 Alton Street | DW_00005_264 |  | CW2 7RT |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443700312 | 489493572844 | Joseph Westwood Mar 6, 2026 2:05 PM
27 Barnabas Avenue | DW_00023_27 |  | CW1 3NS |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443710363 | 489309331680 | Joseph Westwood Mar 6, 2026 2:05 PM
27 Bowen Cooke Avenue | DW_00020_27 |  | CW1 3NR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689233 | 489399770332 | Joseph Westwood Mar 6, 2026 2:05 PM
27 Goulden Street | DW_00029_27 |  | CW1 3LB |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443693125 | 489511535826 | Joseph Westwood Mar 6, 2026 2:05 PM
27 Wallfields Road | DW_00408_27 |  | CW5 5NT |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683914 | 489620519156 | Joseph Westwood Mar 6, 2026 2:05 PM
27 Weaver Road | DW_00403_27 |  | CW5 5NP |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683935 | 489609730258 | Joseph Westwood Mar 6, 2026 2:05 PM
274 Alton Street | DW_00005_274 |  | CW2 7RT |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683667 | 489620519157 | Joseph Westwood Mar 6, 2026 2:05 PM
28 Frank Webb Avenue | DW_00019_28 |  | CW1 3NH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443710686 | 489625915621 | Joseph Westwood Mar 6, 2026 2:05 PM
284 Alton Street | DW_00005_284 |  | CW2 7RY |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692915 | 489525670127 | Joseph Westwood Mar 6, 2026 2:05 PM
29 Barnabas Avenue | DW_00023_29 |  | CW1 3NS |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689613 | 488150739159 | Joseph Westwood Mar 6, 2026 2:05 PM
29 Frank Webb Avenue | DW_00019_29 |  | CW1 3NH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689438 | 489609730256 | Joseph Westwood Mar 6, 2026 2:04 PM
29 Wallfields Road | DW_00408_29 |  | CW5 5NT |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443693359 | 489282400464 | Joseph Westwood Mar 6, 2026 2:04 PM
3 Stewart Street | DW_00214_3 |  | CW2 7RW |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443700307 | 488447249620 | Joseph Westwood Mar 6, 2026 2:04 PM
30 Frank Webb Avenue | DW_00019_30 |  | CW1 3NH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692354 | 489379949780 | Joseph Westwood Mar 6, 2026 2:05 PM
30 Kettell Avenue | DW_00024_30 |  | CW1 3NJ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683769 | 488354188499 | Joseph Westwood Mar 6, 2026 2:05 PM
31 Barnabas Avenue | DW_00023_31 |  | CW1 3NS |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692987 | 489542931703 | Joseph Westwood Mar 6, 2026 2:05 PM
31 Lime Tree Avenue | DW_00055_31 |  | CW1 4HN |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692425 | 489282400467 | Joseph Westwood Mar 6, 2026 2:05 PM
31 Pear Tree Avenue | DW_00028_31 |  | CW1 3SH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683909 | 489627713773 | Joseph Westwood Mar 6, 2026 2:05 PM
31 Wallfields Road | DW_00408_31 |  | CW5 5NT |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683858 | 489506116843 | Joseph Westwood Mar 6, 2026 2:05 PM
32 Goulden Street | DW_00029_32 |  | CW1 3LA |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692827 | 488354188501 | Joseph Westwood Mar 6, 2026 2:05 PM
32 Victoria Avenue | DW_00012_32 |  | CW2 7SQ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692706 | 489569618107 | Joseph Westwood Mar 6, 2026 2:05 PM
320 Alton Street | DW_00005_320 |  | CW2 7RY |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692540 | 488845191405 | Joseph Westwood Mar 6, 2026 2:05 PM
33 Bowen Cooke Avenue | DW_00020_33 |  | CW1 3NR |  |  | https://pashub.net/jobs/10de9def-4a6e-4264-9062-7d74afc7938d/details | TGP- Atkins |  | jak.wells@domna.homes | 2026-03-23 | Completed & Uploaded | [6 empty] | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11443689469 | 489618721004 | Joseph Westwood Mar 6, 2026 2:05 PM
33 Osborne Grove | DW_00515_33 |  | CW2 5BY |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443693165 | 489329156302 | Joseph Westwood Mar 6, 2026 2:05 PM
34 Barnabas Avenue | DW_00023_34 |  | CW1 3NS |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683501 | 489548245187 | Joseph Westwood Mar 6, 2026 2:05 PM
34 Bowen Cooke Avenue | DW_00020_34 |  | CW1 3NR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443693480 | 489571412161 | Joseph Westwood Mar 6, 2026 2:05 PM
34 Pyrus Avenue | DW_00069_34 |  | CW1 4EY |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443693185 | 488190636259 | Joseph Westwood Mar 6, 2026 2:05 PM
34 Warmingham Road | DW_00189_34 |  | CW1 4PU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443693854 | 489616921810 | Joseph Westwood Mar 6, 2026 2:05 PM
349 Alton Street | DW_00005_349 |  | CW2 7RS |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692906 | 489500760290 | Joseph Westwood Mar 6, 2026 2:05 PM
35 Barnabas Avenue | DW_00023_35 |  | CW1 3NS |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443684151 | 489618721008 | Joseph Westwood Mar 6, 2026 2:05 PM
35 Cartwright Road | DW_00545_35 |  | CW1 5RP |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689467 | 489618721005 | Joseph Westwood Mar 6, 2026 2:04 PM
35 Frank Webb Avenue | DW_00019_35 |  | CW1 3NH |  |  |  | TGP- Atkins |  | abdul.koddus@domna.homes | 2026-03-17 | Completed & Uploaded | 58 | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692823 | 488354188503 | Joseph Westwood Mar 6, 2026 2:04 PM
36 Bowen Cooke Avenue | DW_00020_36 |  | CW1 3NR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689690 | 489468434635 | Joseph Westwood Mar 6, 2026 2:04 PM
36 Davenham Crescent | DW_00009_36 |  | CW2 7RZ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683713 | 489468434634 | Joseph Westwood Mar 6, 2026 2:05 PM
36 Kettell Avenue | DW_00024_36 |  | CW1 3NJ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683409 | 489282400468 | Joseph Westwood Mar 6, 2026 2:05 PM
37 Frank Webb Avenue | DW_00019_37 |  | CW1 3NH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689173 | 489493572842 | Joseph Westwood Mar 6, 2026 2:05 PM
37 St Marys Road | DW_00407_37 |  | CW5 5NU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683817 | 489627713771 | Joseph Westwood Mar 6, 2026 2:05 PM
38 Kettell Avenue | DW_00024_38 |  | CW1 3NL |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689866 | 489569618109 | Joseph Westwood Mar 6, 2026 2:05 PM
389 Alton Street | DW_00005_389 |  | CW2 7RT |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689609 | 489520401632 | Joseph Westwood Mar 6, 2026 2:05 PM
39 Cartwright Road | DW_00545_39 |  | CW1 5RP |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692826 | 488354188500 | Joseph Westwood Mar 6, 2026 2:05 PM
4 Almond Avenue | DW_00061_4 |  | CW1 4DZ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443684148 | 489511535828 | Joseph Westwood Mar 6, 2026 2:05 PM
4 Barnabas Avenue | DW_00023_4 |  | CW1 3NS |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683715 | 489644164289 | Joseph Westwood Mar 6, 2026 2:05 PM
4 Bowen Cooke Avenue | DW_00020_4 |  | CW1 3NR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443700314 | 489613324478 | Joseph Westwood Mar 6, 2026 2:05 PM
4 Cartwright Road | DW_00545_4 |  | CW1 5RP |  |  | https://pashub.net/jobs/da531bc6-3290-45af-b39b-6699e741e4c2/details | TGP- Atkins |  | adam.barlow@domna.homes | 2026-03-25 | Completed & Uploaded | [6 empty] | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11443692586 | 489511535827 | Joseph Westwood Mar 6, 2026 2:05 PM
4 Casey Lane | DW_00554_4 |  | CW2 5NH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689693 | 488197937361 | Joseph Westwood Mar 6, 2026 2:05 PM
4 Crowton Cottages | DW_00536_4 |  | CW7 4DP |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689379 | 488354188502 | Joseph Westwood Mar 6, 2026 2:05 PM
4 Frank Webb Avenue | DW_00019_4 |  | CW1 3NH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443700338 | 489622323428 | Joseph Westwood Mar 6, 2026 2:05 PM
4 St Marys Road | DW_00407_4 |  | CW5 5NU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443700487 | 489609730260 | Joseph Westwood Mar 6, 2026 2:05 PM
40 Bowen Cooke Avenue | DW_00020_40 |  | CW1 3NR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683936 | 489625915620 | Joseph Westwood Mar 6, 2026 2:05 PM
40 Davenham Crescent | DW_00009_40 |  | CW2 7RZ |  |  | https://pashub.net/jobs/36c84d69-1bf8-4c0f-a439-cf219ce49cf8/details | TGP- Atkins |  | abdul.koddus@domna.homes | 2026-03-25 | Completed & Uploaded | [6 empty] | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11443683983 | 489399770330 | Joseph Westwood Mar 6, 2026 2:05 PM
41 Cartwright Road | DW_00545_41 |  | CW1 5RP |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443690296 | 489542931704 | Joseph Westwood Mar 6, 2026 2:04 PM
419 Alton Street | DW_00005_419 |  | CW2 7RX |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443691045 | 489627713775 | Joseph Westwood Mar 6, 2026 2:04 PM
42 Albion Street | DW_00040_42 |  | CW2 8NG |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443690250 | 489588149454 | Joseph Westwood Mar 6, 2026 2:04 PM
427 Alton Street | DW_00005_427 |  | CW2 7RX |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443663948 | 489644164292 | Joseph Westwood Mar 6, 2026 2:05 PM
44 Bowen Cooke Avenue | DW_00020_44 |  | CW1 3NR |  |  | https://pashub.net/jobs/dba849cc-11e6-4ecb-aad1-82ae968fc5f6/details | TGP- Atkins |  | abdul.koddus@domna.homes | 2026-03-16 | Completed & Uploaded | D62 | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443684983 | 488447249621 | Joseph Westwood Mar 6, 2026 2:05 PM
44 Osborne Grove | DW_00515_44 |  | CW2 5BY |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443679699 | 488190636258 | Joseph Westwood Mar 6, 2026 2:05 PM
441 Alton Street | DW_00005_441 |  | CW2 7RX |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443679307 | 488845191406 | Joseph Westwood Mar 6, 2026 2:05 PM
448 Underwood Lane | DW_00014_448 |  | CW1 3SF |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443705177 | 489399770329 | Joseph Westwood Mar 6, 2026 2:05 PM
46 Bowen Cooke Avenue | DW_00020_46 |  | CW1 3NR |  |  | https://pashub.net/jobs/c76a0801-2814-4a64-8997-7b5da8a06e26/details | TGP- Atkins |  | abdul.koddus@domna.homes | 2026-03-19 | Completed & Uploaded | D67 | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443684306 | 489613324480 | Joseph Westwood Mar 6, 2026 2:05 PM
46 Kettell Avenue | DW_00024_46 |  | CW1 3NL |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443684266 | 489566047468 | Joseph Westwood Mar 6, 2026 2:05 PM
46 Osborne Grove | DW_00515_46 |  | CW2 5BY |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443679308 | 489379949777 | Joseph Westwood Mar 6, 2026 2:05 PM
47 Manor Road North | DW_00409_47 |  | CW5 5NW |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443690501 | 488421613775 | Joseph Westwood Mar 6, 2026 2:05 PM
476 Underwood Lane | DW_00014_476 |  | CW1 3SG |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443698614 | 489613324481 | Joseph Westwood Mar 6, 2026 2:05 PM
478 Underwood Lane | DW_00014_478 |  | CW1 3SG |  |  |  | TGP- Atkins |  | adam.barlow@domna.homes | 2026-03-18 | Completed & Uploaded | 66 | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443685087 | 489569617145 | Joseph Westwood Mar 6, 2026 2:05 PM
48 Frank Webb Avenue | DW_00019_48 |  | CW1 3NH |  |  | https://pashub.net/jobs/ad615495-c7ea-46f4-8798-40160cd1cd4b/details | TGP- Atkins |  | abdul.koddus@domna.homes | 2026-03-17 | Completed & Uploaded | D57 | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443690735 | 489468434638 | Joseph Westwood Mar 6, 2026 2:05 PM
482 Underwood Lane | DW_00014_482 |  | CW1 3SG |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443691099 | 489509765365 | Joseph Westwood Mar 6, 2026 2:05 PM
486 Underwood Lane | DW_00014_486 |  | CW1 3SG |  |  |  | TGP- Atkins |  | adam.barlow@domna.homes | 2026-03-19 | Completed & Uploaded | 54E | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443690373 | 489509765364 | Joseph Westwood Mar 6, 2026 2:05 PM
488 Underwood Lane | DW_00014_488 |  | CW1 3SG |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443679583 | 489309331678 | Joseph Westwood Mar 6, 2026 2:05 PM
49 Church Lane | DW_00501_49 |  | CW2 8HA |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443684308 | 489609730257 | Joseph Westwood Mar 6, 2026 2:05 PM
490 Underwood Lane | DW_00014_490 |  | CW1 3SG |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443690736 | 488103438537 | Joseph Westwood Mar 6, 2026 2:05 PM
494 Underwood Lane | DW_00014_494 |  | CW1 3SQ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443695103 | 489645958383 | Joseph Westwood Mar 6, 2026 2:04 PM
5 Cartwright Road | DW_00545_5 |  | CW1 5RP |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443676166 | 489616921809 | Joseph Westwood Mar 6, 2026 2:04 PM
5 Frank Webb Avenue | DW_00019_5 |  | CW1 3NH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443708730 | 489500760292 | Joseph Westwood Mar 6, 2026 2:04 PM
5 Pyms Lane | DW_00027_5 |  | CW1 3PJ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443694790 | 489588149455 | Joseph Westwood Mar 6, 2026 2:05 PM
510 West Street | DW_00011_510 |  | CW2 8SG |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443695200 | 489613324483 | Joseph Westwood Mar 6, 2026 2:05 PM
516 Underwood Lane | DW_00014_516 |  | CW1 3SQ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443694987 | 489618721015 | Joseph Westwood Mar 6, 2026 2:05 PM
52 Davenham Crescent | DW_00009_52 |  | CW2 7RZ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443681702 | 489511535830 | Joseph Westwood Mar 6, 2026 2:05 PM
52 Kettell Avenue | DW_00024_52 |  | CW1 3NL |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443695154 | 489500760294 | Joseph Westwood Mar 6, 2026 2:05 PM
526 West Street | DW_00011_526 |  | CW2 8SG |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443687173 | 489627713774 | Joseph Westwood Mar 6, 2026 2:05 PM
528 West Street | DW_00011_528 |  | CW2 8SG |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443687489 | 489332752626 | Joseph Westwood Mar 6, 2026 2:05 PM
530 Underwood Lane | DW_00014_530 |  | CW1 3SQ |  |  |  | TGP- Atkins |  | adam.barlow@domna.homes | 2026-03-19 | Completed & Uploaded | 54E | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443694495 | 489609730259 | Joseph Westwood Mar 6, 2026 2:05 PM
554 West Street | DW_00011_554 |  | CW2 8SJ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443687175 | 489509765361 | Joseph Westwood Mar 6, 2026 2:05 PM
56 Bowen Cooke Avenue | DW_00020_56 |  | CW1 3NR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443694670 | 489618721011 | Joseph Westwood Mar 6, 2026 2:05 PM
56 Pyrus Avenue | DW_00069_56 |  | CW1 4EY |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443686853 | 489644164291 | Joseph Westwood Mar 6, 2026 2:05 PM
589 West Street | DW_00011_589 |  | CW2 8SH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443681528 | 489329156297 | Joseph Westwood Mar 6, 2026 2:05 PM
59 Albion Street | DW_00040_59 |  | CW2 8NG |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443695257 | 488421613774 | Joseph Westwood Mar 6, 2026 2:05 PM
59 Plane Tree Drive | DW_00068_59 |  | CW1 4ET |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443695106 | 489606134990 | Joseph Westwood Mar 6, 2026 2:05 PM
595 West Street | DW_00011_595 |  | CW2 8SH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443687045 | 489379949781 | Joseph Westwood Mar 6, 2026 2:05 PM
6 Barnabas Avenue | DW_00023_6 |  | CW1 3NS |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443675983 | 489589945570 | Joseph Westwood Mar 6, 2026 2:05 PM
6 Cartwright Road | DW_00545_6 |  | CW1 5RP |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443694877 | 489589945569 | Joseph Westwood Mar 6, 2026 2:05 PM
6 Malbank | DW_00405_6 |  | CW5 5LU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689689 | 489620519158 | Joseph Westwood Mar 6, 2026 2:04 PM
6 St Marys Road | DW_00407_6 |  | CW5 5NU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443694019 | 489525670128 | Joseph Westwood Mar 6, 2026 2:04 PM
60 Bowen Cooke Avenue | DW_00020_60 |  | CW1 3NR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692619 | 489468434640 | Joseph Westwood Mar 6, 2026 2:04 PM
601 West Street | DW_00011_601 |  | CW2 8SH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443700447 | 489622323425 | Joseph Westwood Mar 6, 2026 2:05 PM
65 Albion Street | DW_00040_65 |  | CW2 8NG |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443702685 | 489616921811 | Joseph Westwood Mar 6, 2026 2:05 PM
66 Frank Webb Avenue | DW_00019_66 |  | CW1 3NH |  |  |  | TGP- Atkins |  | abdul.koddus@domna.homes | 2026-03-17 | Completed & Uploaded | 59 | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692988 | 489518618873 | Joseph Westwood Mar 6, 2026 2:05 PM
68 Frank Webb Avenue | DW_00019_68 |  | CW1 3NQ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443693182 | 488447249619 | Joseph Westwood Mar 6, 2026 2:05 PM
68 Kettell Avenue | DW_00024_68 |  | CW1 3NL |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443700335 | 489336351958 | Joseph Westwood Mar 6, 2026 2:05 PM
7 French Lane End | DW_00564_7 |  | CW5 8AP |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683714 | 489611525369 | Joseph Westwood Mar 6, 2026 2:05 PM
7 Malbank | DW_00405_7 |  | CW5 5LU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683571 | 489613324479 | Joseph Westwood Mar 6, 2026 2:05 PM
7 Prince Edward Street | DW_00402_7 |  | CW5 5NR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443693848 | 489618721013 | Joseph Westwood Mar 6, 2026 2:05 PM
7 Pyms Lane | DW_00027_7 |  | CW1 3PJ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443694023 | 489468434637 | Joseph Westwood Mar 6, 2026 2:05 PM
7 Weaver Road | DW_00403_7 |  | CW5 5NJ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443710364 | 489329156298 | Joseph Westwood Mar 6, 2026 2:05 PM
70 Kettell Avenue | DW_00024_70 |  | CW1 3NL |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683773 | 488197937363 | Joseph Westwood Mar 6, 2026 2:05 PM
71 Bradfield Road | DW_00015_71 |  | CW1 3RB |  |  |  | TGP- Atkins |  | adam.barlow@domna.homes | 2026-03-18 | Completed & Uploaded | 54E | [5 empty] | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11443692855 | 489622323426 | Joseph Westwood Mar 6, 2026 2:05 PM
75 Crewe Road | DW_00547_75 |  | CW1 5QX |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683860 | 489282400466 | Joseph Westwood Mar 6, 2026 2:05 PM
8 Vauxhall Road | DW_00406_8 |  | CW5 5QR |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443693853 | 489644164290 | Joseph Westwood Mar 6, 2026 2:05 PM
8 White Avenue | DW_00013_8 |  | CW2 7SH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443683503 | 489332752629 | Joseph Westwood Mar 6, 2026 2:05 PM
83 Bradfield Road | DW_00015_83 |  | CW1 3RB |  |  |  | TGP- Atkins |  | adam.barlow@domna.homes | 2026-03-18 | Completed & Uploaded | 56D | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443692958 | 489618721007 | Joseph Westwood Mar 6, 2026 2:05 PM
84 Kettell Avenue | DW_00024_84 |  | CW1 3NL |  |  |  | TGP- Atkins |  | abdul.koddus@domna.homes | 2026-03-18 | Completed & Uploaded | 56D | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443689802 | 489645958382 | Joseph Westwood Mar 6, 2026 2:05 PM
85 Lime Tree Avenue | DW_00055_85 |  | CW1 4HL |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443681361 | 489618721016 | Joseph Westwood Mar 6, 2026 2:04 PM
87 Ford Lane | DW_00026_87 |  | CW1 3EH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443681537 | 489518619836 | Joseph Westwood Mar 6, 2026 2:04 PM
88 Frank Webb Avenue | DW_00019_88 |  | CW1 3NQ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443694913 | 489622323427 | Joseph Westwood Mar 6, 2026 2:04 PM
9 Arderne Avenue | DW_00088_9 |  | CW2 8NS |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443687041 | 489611525368 | Joseph Westwood Mar 6, 2026 2:05 PM
9 Kettell Avenue | DW_00024_9 |  | CW1 3NJ |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443687488 | 489627713776 | Joseph Westwood Mar 6, 2026 2:05 PM
9 Malbank | DW_00405_9 |  | CW5 5LU |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443687043 | 489511535831 | Joseph Westwood Mar 6, 2026 2:05 PM
9 Pear Tree Avenue | DW_00028_9 |  | CW1 3SH |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443676168 | 489332752628 | Joseph Westwood Mar 6, 2026 2:05 PM
9 Peel Square | DW_00231_9 |  | CW1 3BW |  |  |  | TGP- Atkins |  | abdul.koddus@domna.homes | 2026-03-18 | Completed & Uploaded | 57D | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443686431 | 489309331681 | Joseph Westwood Mar 6, 2026 2:05 PM
9 Victoria Avenue | DW_00012_9 |  | CW2 7SG |  |  |  | TGP- Atkins |  |  |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443681190 | 489569618108 | Joseph Westwood Mar 6, 2026 2:05 PM
97 Bradfield Road | DW_00015_97 |  | CW1 3RB |  |  |  | TGP- Atkins |  | abdul.koddus@domna.homes | 2026-03-18 | Completed & Uploaded | 54E | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11443681495 | 488190636260 | Joseph Westwood Mar 6, 2026 2:05 PM
71 Cheshire Street Crewe Cheshire | DW_00585_71 |  | CW3 0HB |  |  |  | TGP- Atkins | PasHub | Domna |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11302955548 | 473599409377 | Joseph Westwood Feb 18, 2026 12:10 PM |  | Working on it
2 Cedar Court Nantwich Cheshire | DW_00513_2 |  | CW5 6RB |  |  | https://pashub.net/jobs/a3566f71-dc74-46a8-ba8c-904ae0ede476/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 |  | Client query |  | Debbie Langer |  | Queries & issues | Property already has Solar on it- electric boiler, this would need an ASHP or radbots installed to get C. | [20 empty] | Outstanding | [34 empty] | 11302966919 | 473407281341 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed | Working on it
12 Queen Street, Tarporley, Cheshire | DW_00529_12 |  | CW6 9QY |  |  | https://pashub.net/jobs/b17afa78-8382-41dd-993e-b95e751460fb/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 |  | Client query |  | Jalwinder Singh |  | Queries & issues | Property already has SPV installed on the rear of the elevation, CWI filled, Loft insulation is adequate, ashp already in situ. Could upgrade ASHP ? Or just add insulation to Cylinder. Starting SAP score is 68. | [20 empty] | Outstanding | [34 empty] | 11315345524 | 493076806868 | Joseph Westwood Feb 19, 2026 2:56 PM
161 Cobbs Lane Crewe Cheshire | DW_00558_161 | Shavington | CW2 5JL | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/2d680082-4d1b-4ed9-a6b3-d45a656f3b2c/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 56 |  | Client query |  | Debbie Langer | 2026-03-11 | Queries & issues | Property has SPV already installed on the front elevation of the property, loft insulation is adequate, solid brick construction. Deb to review | [20 empty] | Outstanding | [34 empty] | 11302955336 | 473398223082 | Joseph Westwood Feb 18, 2026 12:10 PM |  |  | Cracking on internal walls in bathroom and utility, Pointing up required around rear elevation.
73 Cheshire Street Crewe Cheshire | DW_00585_73 |  | CW3 0HB |  |  |  | TGP- Atkins | PasHub | Domna |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11302957620 | 473692248275 | Joseph Westwood Feb 18, 2026 12:10 PM |  | Working on it
8 St James Close Crewe Cheshire | DW_00611_8 |  | CW3 0BD | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/6937640d-f499-4523-2496-08ddf038716d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 55 |  | Client query |  | Debbie Langer |  | Queries & issues | Borescope survey / evidence is required as RA has stated CWI is unfilled. loft insulation is adequate, Starting SAP score 55. Deb to review | [20 empty] | Outstanding | [34 empty] | 11302951290 | 473692248274 | Joseph Westwood Feb 18, 2026 12:10 PM |  |  | Damp brickwork as a result of a leaking down pipe on the rear elevation.
4 The Homesteads Nantwich Cheshire | DW_00600_4 |  | CW5 6DZ |  |  |  | TGP- Atkins | PasHub | Domna |  | Outstanding | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11302951731 | 473695846608 | Joseph Westwood Feb 18, 2026 12:10 PM |  | Working on it
2 Oakfield Avenue Nantwich Cheshire | DW_00572_2 |  | CW5 8ER | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/db6c3f3b-d739-4726-ab2b-ac9b292c05f1/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 55 |  | Client query |  | Debbie Langer | 2026-03-11 | Queries & issues | Unable to achieve a C, loft insulation is adequate, CWI is filled. Starting SAP score 55. Unable to add ( Radbots) as property has heat pump already installed. ASHP would need replacing with newer model. Or at least 3. 5KW | [20 empty] | Outstanding | [34 empty] | 11302955235 | 472892711138 | Joseph Westwood Feb 18, 2026 12:10 PM
4 Crosslands, Crewe | DW_00552_4 |  | CW1 5TG |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 59 | [5 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11315340676 | 492935229689 | Joseph Westwood Feb 19, 2026 2:56 PM
16 Chapel Close, Winsford, Cheshire | DW_00537_16 |  | CW7 4DT |  |  | https://pashub.net/jobs/01d78632-fb87-44f2-aa8c-415f347cbf44/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 36 |  | Batch 6 |  | Saskia Ratcliff |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315328684 | 492641728706 | Joseph Westwood Feb 19, 2026 2:56 PM
5 Queens Crescent, Crewe, Cheshire | DW_00601_5 |  | CW1 4RB |  |  | https://pashub.net/jobs/2918a843-f4e1-442c-af53-1bc6296a961a/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 35 |  | Batch 6 |  | Saskia Ratcliff |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315357702 | 493004767451 | Joseph Westwood Feb 19, 2026 2:56 PM
18 Church Row, Tarporley, Cheshire | DW_00527_18 |  | CW6 9PL |  |  | https://pashub.net/jobs/a117ec8d-a9f8-40d8-9cee-e81585258e7c/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 29 |  | Batch 6 |  | Saskia Ratcliff |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315336344 | 492035929276 | Joseph Westwood Feb 19, 2026 2:56 PM
13 Sandfield Avenue Wrenbury | DW_00571_13 |  | CW5 8EU |  |  | https://pashub.net/jobs/68496525-ddb9-4935-9bb3-3341674b80d1/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 28 |  | Batch 6 |  | Saskia Ratcliff |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11302954923 | 473690375360 | Joseph Westwood Feb 18, 2026 12:10 PM
3 Queens Crescent, Crewe, Cheshire | DW_00601_3 |  | CW1 4RB |  |  | https://pashub.net/jobs/37879d0b-db5a-4fef-9013-005703c69016/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 27 |  | Batch 6 |  | Saskia Ratcliff |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315321029 | 493121076433 | Joseph Westwood Feb 19, 2026 2:56 PM
8 East Avenue Crewe Cheshire | DW_00555_8 | Shavington | CW2 5LZ |  |  | https://pashub.net/jobs/02e191a6-a6dc-4d9c-a205-73ca911ea367/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 53 |  | Batch 6 | Hubspot view | Debbie Langer |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11302943122 | 473608458471 | Joseph Westwood Feb 18, 2026 12:10 PM
5 Weaver View Nantwich Cheshire | DW_00599_5 |  | CW5 6EB |  |  | https://pashub.net/jobs/29a4a029-a10f-494b-a42d-299bdbc9ced5/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 52 |  | Batch 6 | Hubspot view | Debbie Langer |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11302951240 | 473686791414 | Joseph Westwood Feb 18, 2026 12:10 PM
4 Festival Avenue Crewe Cheshire | DW_00588_4 |  | CW3 0DB |  |  | https://pashub.net/jobs/93e78bed-02cf-4646-2631-08ddf038716d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 52 |  | Batch 6 | Hubspot view | Debbie Langer |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11302951732 | 473683124465 | Joseph Westwood Feb 18, 2026 12:10 PM
39 Waterloo Road, Crewe, Cheshire | DW_00551_39 |  | CW1 5TF |  |  | https://pashub.net/jobs/840082ed-53bc-432d-837a-9fbe1de51830/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 40 |  | Batch 6 |  | Debbie Langer |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315357348 | 492953213160 | Joseph Westwood Feb 19, 2026 2:56 PM
2 Tarvin Avenue Crewe Cheshire | DW_00113_2 |  | CW2 8TQ | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/6bba9e13-bc6e-42c8-bce6-8f4594cea9df/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | C74 | Batch 1 |  | Debbie Langer | 2026-02-19 | (V1) IOE/MTP Complete | 2KW PV SW | Evidence of damp or mould growth. | 2026-02-19 |  | V1 Uploaded | DMevs, Solar PV, Loft insulation |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | H01S900 | Uploaded | 2026-02-24 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302957280 | 473398223084 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Some mould in wetrooms, some repairs needed on rafters in loft- Modellled on assessor hub.
2 Doddington Road Crewe Cheshire | DW_00077_2 |  | CW2 8ND | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/648db24d-5c80-4a2a-8156-300895bd4fc9/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | C78 | Batch 1 |  | Debbie Langer | 2026-02-19 | (V1) IOE/MTP Complete | 2KW SW PV |  | 2026-02-19 |  | V1 Uploaded | DMevs, Solar PV, Loft insulation |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | B01S703 | Uploaded | 2026-02-24 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302967812 | 473291099348 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
23 Doddington Road Crewe Cheshire | DW_00077_23 |  | CW2 8NQ | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/2061f4a6-8f1e-426d-be0d-69f127a1bb72/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | C78 | Batch 1 |  | Debbie Langer | 2026-02-19 | (V1) IOE/MTP Complete | 2.0KW SW |  | 2026-02-19 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | B01S705 | Uploaded | 2026-02-24 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302967286 | 473529242841 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
34 Beech Drive Crewe Cheshire | DW_00503_34 |  | CW2 8RE | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/e59e3e3a-f384-4c54-8d3d-271f2faf7f1a/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | C78 | Batch 1 |  | Debbie Langer | 2026-02-19 | (V1) IOE/MTP Complete | 2.5KW SE | Evidence of damp or mould growth. | 2026-02-19 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-02-27 |  | Programmed |  | H02S900 | Uploaded | 2026-03-04 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302953941 | 472653891776 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Signs of rising damp under the window in bedroom one, please see photos for evidence. There is a hole in the ceiling in the hallway, this is due to a boiler leak which is still ongoing.
36 Albion Street Crewe Cheshire | DW_00040_36 |  | CW2 8NG | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/42a4c6fe-a6b6-4cd9-a9ec-3eb19c145ae7/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | C79 | Batch 1 |  | Debbie Langer | 2026-02-19 | (V1) IOE/MTP Complete | 2.0KW SE |  | 2026-02-19 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  | dMEV, no mould but existing EWI. | Programmed |  | B01S702 | Uploaded | 2026-02-24 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302943300 | 473601265903 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
18 Somerford Avenue Crewe Cheshire | DW_00079_18 |  | CW2 8NE | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/eee50ff1-e1af-4187-9e2b-427e5f0b6d57/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | C74 | Batch 1 |  | Debbie Langer | 2026-02-19 | (V1) IOE/MTP Complete | 2 KW SE | Evidence of damp or mould growth. | 2026-02-19 |  | V1 Uploaded | DMevs, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | B01S708 | Uploaded | 2026-02-24 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302940782 | 473690409187 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Mould visible on bathroom ceiling where the tiles meet the ceiling see photos in condensation and mould picture field.
4 Darley Avenue Crewe Cheshire | DW_00080_4 |  | CW2 8NF | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/99e2ce56-4bda-47f0-bdff-7404c6b9e278/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | C78 | Batch 1 |  | Jalwinder Singh | 2026-02-24 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-23 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-02-27 |  | Programmed |  | B01S713 | Uploaded | 2026-02-27 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302951239 | 472653891778 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
82 Marshfield Avenue Crewe Cheshire | DW_00111_82 |  | CW2 8TE | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/8564684a-b2af-4406-b205-ce77ce10a62e/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 67 | C77 | Batch 1 |  | Debbie Langer | 2026-02-20 | (V1) IOE/MTP Complete | 2KW SE |  | 2026-02-20 |  | V1 Uploaded | DMevs, Solar PV, Loft insulation |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-02-27 |  | Programmed |  | H01S905 | Uploaded | 2026-02-27 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302966935 | 473383802099 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Roof felting coming away- in a poor state
11 Doddington Road Crewe Cheshire | DW_00077_11 |  | CW2 8ND | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/7d3f0020-ff5b-458f-997c-3db4e1dbc999/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 67 | C77 | Batch 1 |  | Debbie Langer | 2026-02-20 | (V1) IOE/MTP Complete | 2kw SW- | Evidence of damp or mould growth. | 2026-02-20 |  | V1 Uploaded | DMevs, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | B01S704 | Uploaded | 2026-02-24 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302951488 | 473282284755 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Visible mould around windows in bedrooms one and bedroom two also visible on internal wall adjacent the bathroom in bedroom three and on ceiling in bedroom free see photos in internal wall picture field and condensation and mould picture field.
8 Somerford Avenue Crewe Cheshire | DW_00079_8 |  | CW2 8NE | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/8b3c7834-c207-4203-92e9-506dbf8b81b5/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 67 | C77 | Batch 1 |  | Debbie Langer | 2026-02-20 | (V1) IOE/MTP Complete | 2KW SW |  | 2026-02-20 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | B01S707 | Uploaded | 2026-02-24 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302957795 | 473523861722 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
43 Albion Street Crewe Cheshire | DW_00040_43 |  | CW2 8NG | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/9c66055f-4a7a-474d-8927-600707540df9/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 67 | C77 | Batch 1 |  | Debbie Langer | 2026-02-20 | (V1) IOE/MTP Complete | 2.5.KW PV modelled | Evidence of damp or mould growth. | 2026-02-20 |  | V1 Uploaded | DMevs, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | B01S701 | Uploaded | 2026-02-24 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302951326 | 473674035405 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | -Mould appearing on kitchen ceiling and around windows in bed 1 bed 2 and living room please see condition photos
2 Gawsworth Avenue Crewe Cheshire | DW_00094_2 |  | CW2 8PB | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/6cb447e9-ad48-49bc-ae6a-0caf81495597/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | C78 | Batch 1 |  | Jalwinder Singh | 2026-02-23 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-02-23 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-02-27 |  | Programmed |  | H04S900 | Uploaded | 2026-02-27 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302957523 | 473674035406 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
5 Darley Avenue Crewe Cheshire | DW_00080_5 |  | CW2 8NF | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/17df2858-f302-413d-b2c4-e442bf7e12c5/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | C76 | Batch 1 |  | Debbie Langer | 2026-02-23 | (V1) IOE/MTP Complete | 2.0KW SE PV |  | 2026-02-23 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-02-27 |  | Programmed |  | B01S711 | Uploaded | 2026-02-27 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302943461 | 473593933024 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
48 Barthomley Crescent Crewe Cheshire | DW_00110_48 |  | CW2 8TP | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/0b117eac-48f7-4e26-a331-23c8189472dc/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | C77 | Batch 1 |  | Debbie Langer | 2026-02-23 | (V1) IOE/MTP Complete | 2.0KW SE PV |  | 2026-02-23 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-02-27 |  | Programmed |  | H01S906 | Uploaded | 2026-02-27 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302973095 | 473674035407 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
39 Rockwood Avenue, Crewe, Cheshire, | DW_00006_39 |  | CW2 8LU | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/657ae9ab-e4d8-430d-96da-5c07f8323fd9/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | C77 | Batch 1 |  | Jalwinder Singh | 2026-02-23 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-23 |  | V1 Uploaded | Solar PV, DMevs, Loft insulation |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-02-27 |  | Programmed |  | H06E900 | Uploaded | 2026-02-27 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302955125 | 473677717722 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
29 Doddington Road Crewe Cheshire | DW_00077_29 |  | CW2 8NQ | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/4457314a-8c05-4167-a5ce-ccd65c924704/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | C77 | Batch 1 |  | Jalwinder Singh | 2026-02-23 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-23 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  | NO extract Kitchen, No working bathroom, dMEV, no mould but existing EWI. | Programmed |  | B01S706 | Uploaded | 2026-02-24 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302955236 | 473694046435 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
24 Rudheath Close Crewe Cheshire | DW_00106_24 |  | CW2 8TL | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/f27d81d2-75ad-4024-899a-c69fce042656/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | C77 | Batch 1 |  | Jalwinder Singh | 2026-02-24 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-24 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-02-27 |  | Programmed |  | H01S901 | Uploaded | 2026-02-27 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302968163 | 473601228993 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Roof condition considered to be poor internally / roof felt none existent, loft guttering and downpipes are also in poor condition.
20 Alvaston Walk Crewe Cheshire | DW_00097_20 |  | CW2 8PZ | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/2d2addf5-ab27-452e-a2b3-2c87cdf60416/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | C81 | Batch 1 |  | Jalwinder Singh | 2026-02-23 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-24 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-02-27 |  | Programmed |  | B03M900 | Uploaded | 2026-02-27 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302943554 | 473681290458 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
2 Somerford Avenue Crewe Cheshire | DW_00079_2 |  | CW2 8NE | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/64e62257-9092-4901-87b7-a01ac729b601/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | C76 | Batch 1 |  | Jalwinder Singh | 2026-02-23 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-24 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-02-27 |  | Programmed |  | B01S709 | Uploaded | 2026-02-27 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302955335 | 473697642712 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
79 Marshfield Avenue Crewe Cheshire | DW_00111_79 |  | CW2 8TE | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/068e954a-1a6d-49b1-81e9-8fa689910a0c/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 65 | C73 | Batch 1 |  | Jalwinder Singh | 2026-02-24 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. | Evidence of damp or mould growth. | 2026-02-24 |  | V1 Uploaded | DMevs, Solar PV, Loft insulation |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-02-27 |  | Programmed |  | H01S904 | Uploaded | 2026-02-27 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302973097 | 473606658292 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Mould growth visible at multiple locations, Ceiling cracked visible in bedroom too and on bay window ceiling in the living room. Incorrect funding mechanism has been selected for the Job.
7 Darley Avenue Crewe Cheshire | DW_00080_7 |  | CW2 8NF | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/2782c0ab-60a3-4d05-8ffe-32f6fbf48119/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 64 | C74 | Batch 1 |  | Jalwinder Singh | 2026-02-24 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-24 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-02-27 |  | Programmed |  | B01S712 | Uploaded | 2026-02-27 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302967813 | 473683153123 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
3 Mulberry Road Crewe Cheshire | DW_00607_3 |  | CW2 8UW | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/bac3312d-43cd-4ea8-7f41-08ddf03e139d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 64 | C77 | Batch 1 |  | Jalwinder Singh | 2026-02-23 | (V1) IOE/MTP Complete | 2 KW PV SE - | Evidence of damp or mould growth. | 2026-02-24 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-02-27 |  | Programmed |  |  | Uploaded | 2026-02-27 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302967314 | 473681290459 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Condensation mould on living room ceiling and around bathroom window, Some cracks on kitchen and bathroom walls by the doors.
20 Somerford Avenue Crewe Cheshire | DW_00079_20 |  | CW2 8NE | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/80d2e19a-8371-490c-8a6a-b8676e9c49a6/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 63 | C76 | Batch 1 |  | Debbie Langer | 2026-02-23 | (V1) IOE/MTP Complete | 2.0 KW PV | Evidence of damp or mould growth. | 2026-02-23 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-02-27 |  | Programmed |  | B01S710 | Uploaded | 2026-02-27 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302934731 | 473400024293 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Mould appearing around bedroom 2 ,living room and bathroom windows please see photos
40 Albion Street Crewe Cheshire | DW_00040_40 |  | CW2 8NG | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/f0ac92bf-a9e4-4d1f-a90d-8341541f7bb2/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 63 | C76 | Batch 1 |  | Debbie Langer | 2026-02-24 | (V1) IOE/MTP Complete | 2.0 KW PV | Evidence of damp or mould growth. | 2026-02-23 |  | V1 Uploaded | DMevs, Solar PV, Loft insulation |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | B01S700 | Uploaded | 2026-02-24 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302955065 | 473529242840 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Mould and damp visible on bedroom one ceiling bedroom two ceiling and bedroom three ceiling see photos in condensation and mould picture field
5 Alvaston Walk Crewe Cheshire | DW_00097_5 |  | CW2 8PY | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/92d4d67e-8669-416d-8203-533b71c0456e/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 63 | C74 | Batch 1 |  | Debbie Langer | 2026-02-23 | (V1) IOE/MTP Complete | 2.KW PV |  | 2026-02-23 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-02-27 |  | Programmed |  | B03M901 | Uploaded | 2026-02-27 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302955340 | 473282284752 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Property needs repairs before Retrofit- Pointing issue to rear of property, please see photos Missing and slipped tiles on roof please see photos also roof felt severely disrupted see photos
70 Beech Drive Crewe Cheshire | DW_00503_70 |  | CW2 8RQ | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/452d9679-0ade-42c2-93ea-a26b5fc681b5/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 63 | C76 | Batch 1 |  | Jalwinder Singh | 2026-02-24 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-23 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-02-27 |  | Programmed |  | B02S900 | Uploaded | 2026-02-27 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302967955 | 473282284751 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
74 Beech Drive Crewe Cheshire | DW_00503_74 |  | CW2 8RQ | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/f1877a10-1f88-4fca-8d3f-195dcd7117e7/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 63 | C77 | Batch 1 |  | Jalwinder Singh | 2026-02-24 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-23 |  | V1 Uploaded | DMevs, Solar PV, Loft insulation |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-02-27 |  | Programmed |  | B02S901 | Uploaded | 2026-02-27 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302952909 | 473529242839 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | both the front and rear elevations of full of moss, not sure why they have such a build-up of moss, but this needs to be looked at". There is a visible structural internal crack in the bathroom.
3 Halton Drive Crewe Cheshire | DW_00107_3 |  | CW2 8TA | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/421642ca-9b0d-4e7a-98d4-b09b06d97a82/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 63 | C73 | Batch 1 |  | Jalwinder Singh | 2026-02-24 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST | Evidence of damp or mould growth. | 2026-02-23 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-02-27 |  | Programmed |  | H01S902 | Uploaded | 2026-02-27 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302973096 | 473690375361 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | The roof is in need of some remedial work internally all the felting is torn and damaged / tiles are collapsing in. The loft is full of stored items and there are some significant cracks in the ceiling in all rooms upstairs, this appears to be putting significant weight on the ceiling. There is mould growth on the walls and ceiling in the bathroom.
35 Marshfield Avenue, Crewe, Cheshire | DW_00111_35 |  | CW2 8TH |  |  | https://pashub.net/jobs/43e13a12-8c06-40ce-abd2-f6703260d936/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 62 | C75 | Batch 1 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-03-17 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Requested |  | H01S906 | Uploaded | 2026-03-19 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11315327032 | 492956783805 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed |  | The roof on the property is considered to be in poor condition.
12 Oakfield Close Nantwich Cheshire | DW_00573_12 |  | CW5 8ET | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/be5ecdb0-0365-4ec2-a008-546fabbad3a0/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | C82 | Batch 2 |  | Jalwinder Singh | 2026-03-02 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-03-02 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-06 |  | Programmed |  | B04S900 | Uploaded | 2026-03-06 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302967315 | 473695846607 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
18 Arnold Street Nantwich Cheshire | DW_00499_18 |  | CW5 5QB | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/fd81c4f0-b130-4ddd-7ff2-08ddf03e139d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | C79 | Batch 2 |  | Jalwinder Singh | 2026-03-03 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-03-03 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-06 |  | Programmed |  | H14M900 | Uploaded | 2026-03-05 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302968159 | 473418139893 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Unable to gain access to loft safely, due to its location.
85 Claughton Avenue Crewe Cheshire | DW_00002_85 |  | CW2 6EY | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/0c1d2d24-61bf-47e9-bbe3-dea8dfbf6308/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 67 | C74 | Batch 2 |  | Jalwinder Singh | 2026-02-27 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-27 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-03 |  | Programmed |  | H08E900 | Uploaded | 2026-03-05 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302951557 | 473291099346 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
62 Weaver Road, Nantwich, Cheshire, | DW_00403_62 |  | CW5 5NP | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/af5cf08f-3df1-4883-0085-08ddf03803e1/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 67 | C76 | Batch 2 |  | Jalwinder Singh | 2026-02-27 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-27 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-03 |  | Programmed |  | H12S800 | Uploaded | 2026-03-05 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302957256 | 473595810023 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
11 Volunteer Fields, Nantwich, Cheshire, | DW_00422_11 |  | CW5 5PP | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/3bf88351-63cd-4480-2510-08ddf038716d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 67 | C76 | Batch 2 |  | Jalwinder Singh | 2026-02-27 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-27 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-03 |  | Programmed |  | H12S801 | Uploaded | 2026-03-05 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302955763 | 473291099350 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
2 South Croft Tarporley Cheshire | DW_00530_2 |  | CW6 9TQ | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/84ba0b33-50f6-4db7-a2de-261b1f36c042/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 67 | C77 | Batch 2 |  | Jalwinder Singh | 2026-03-02 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. | Evidence of damp or mould growth. | 2026-03-02 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-06 |  | Programmed |  | H15S9 | Uploaded | 2026-03-10 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302957232 | 473398223083 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | There are Leaks in chimney stack running through bedroom 2, Kitchen wall is damp from the floor up on wall backing onto hall way, Roof tiles are missing, damaged and un-even roof is in poor condition.
44 Claughton Avenue Crewe Cheshire | DW_00002_44 |  | CW2 6EZ | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/881edff8-173d-4cc7-8851-022a8469dec8/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | C74 | Batch 2 |  | Jalwinder Singh | 2026-02-27 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. | Evidence of damp or mould growth. | 2026-02-27 |  | V1 Uploaded | DMevs, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-02 |  | Programmed |  | H07E900 | Uploaded | 2026-03-05 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302955761 | 473695846606 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Damp / Mould visible on external facing wall in WC.
17 East Avenue Crewe Cheshire | DW_00555_17 | Shavington | CW2 5LZ | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/a615679b-fce9-41a4-9a6d-e0a86e1e2a0b/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | C90 | Batch 2 |  | Jalwinder Singh | 2026-03-03 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-03-03 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-03-06 |  | Programmed |  | B05S903 | Uploaded | 2026-03-06 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302966995 | 473683153122 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
6 Gorsey Bank Crescent Nantwich Cheshire | DW_00596_6 |  | CW5 7LX | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/c6c012eb-d442-4f5f-83c7-3502cd485da1/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | C74 | Batch 2 |  | Jalwinder Singh | 2026-03-03 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. | Evidence of damp or mould growth. | 2026-03-03 |  | V1 Uploaded | DMevs, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-06 |  | Programmed |  | H04S901 | Uploaded | 2026-03-06 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302932395 | 473532834009 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Water leaking through the roof including bed 3, customer states its becoming worse ( RA Notes). Evidence of damp on ceiling.
131 Claughton Avenue Crewe Cheshire | DW_00002_131 |  | CW2 6ET | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/a2314e1f-d83d-4a4e-a4f3-85760d9c0a7a/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 65 | C73 | Batch 2 |  | Jalwinder Singh | 2026-02-27 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-27 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-02 |  | Programmed |  | H08E901 | Uploaded | 2026-03-05 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302957253 | 473540078827 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
5 Santune Court Rope Lane Crewe Cheshire | DW_00613_5 | Shavington | CW2 5DR | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/68057efa-7d1f-4207-8fa6-4556ed277597/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 65 | C77 | Batch 2 |  | Jalwinder Singh | 2026-03-03 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-03-03 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-03-06 |  | Programmed |  | B07E900 | Uploaded | 2026-03-10 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302953511 | 473529242844 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
142 Claughton Avenue Crewe Cheshire | DW_00002_142 |  | CW2 6EY | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/05cb0c24-818d-4987-a589-d5f47ef1c0b8/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 65 | C75 | Batch 2 |  | Jalwinder Singh | 2026-03-03 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-03-03 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-03-06 |  | Programmed |  | H16M900 | Uploaded | 2026-03-06 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302951507 | 473599409379 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
121 Claughton Avenue Crewe Cheshire | DW_00002_121 |  | CW2 6ET | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/fa47137c-b338-4c34-b37e-a58eb78aebad/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 64 | C73 | Batch 2 |  | Jalwinder Singh | 2026-02-27 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-27 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-02 |  | Programmed |  | H09M900 | Uploaded | 2026-03-05 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302951508 | 473378317543 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Several slipped tiles,
89 Marsh Lane Nantwich Cheshire | DW_00430_89 |  | CW5 5LD | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/e60e053a-1dc7-48f8-7ff4-08ddf03e139d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 64 | C73 | Batch 2 |  | Jalwinder Singh | 2026-03-02 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. | Evidence of damp or mould growth. | 2026-03-02 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-03 |  | Programmed |  | H11E900 | Uploaded | 2026-03-05 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302942985 | 473400024292 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Mould growth on kitchen floor as a result of water leaking from sink. Large amount of mould growth on bedroom 3 wall and bathroom ceiling, Condensation mould around bedroom 2 window. Some cracks on the kitchen wall.
57 Main Road Nantwich Cheshire | DW_00598_57 |  | CW5 6DN | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/76a1de82-f0bc-42f8-b1b7-1526ee7ae6aa/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 64 | C72 | Batch 2 |  | Jalwinder Singh | 2026-03-02 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-03-02 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-06 |  | Programmed |  | H15S900 | Uploaded | 2026-03-05 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302953513 | 472653891779 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | External walls are in poor conditions. Utility room ceiling has a large crack visible.
134 Claughton Avenue Crewe Cheshire | DW_00002_134 |  | CW2 6EY | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/86c1670a-8994-4df5-8252-8c7b28e07474/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 64 | C76 | Batch 2 |  | Jalwinder Singh | 2026-03-03 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-03-03 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-03 |  | Programmed |  | H10M900 | Uploaded | 2026-03-05 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302953236 | 473690375363 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | One area of sagging coming from the roof felt.
24 East Avenue Crewe Cheshire | DW_00555_24 | Shavington | CW2 5LZ | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/6d9aa161-a4e7-4bda-87a8-1b243a905af5/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 64 | C74 | Batch 2 |  | Jalwinder Singh | 2026-03-04 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-03-04 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-03-06 |  | Programmed |  | H15S901 | Uploaded | 2026-03-06 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302954926 | 473523861724 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Cracks appearing on bed 2 ceiling, Roof condition is poor, roof felt non-existent .
57 Barons Road, Shavington, Crewe, Cheshire, | DW_00521_57 | Shavington | CW2 5ER | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/f7fbef8e-8e6c-4e36-9304-d992745e8595/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 63 | C73 | Batch 2 |  | Jalwinder Singh | 2026-02-26 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. | Evidence of damp or mould growth. | 2026-02-26 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-02 |  | Programmed |  | B05S900 | Uploaded | 2026-03-05 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302951556 | 472653891775 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Internal gable wall within the living room shows signs of rising damp. Signs of mould / damp growth around the property.
127 Claughton Avenue Crewe Cheshire | DW_00002_127 |  | CW2 6ET | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/cf13b2db-86f2-4c3b-ad0f-b1ec43f9ac9e/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 63 | C74 | Batch 2 |  | Jalwinder Singh | 2026-02-26 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-26 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-02 |  | Programmed |  | H09M901 | Uploaded | 2026-03-05 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302955126 | 473610256610 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Guttering and rainwater goods require attention.
13 Circle Avenue Nantwich Cheshire | DW_00510_13 |  | CW5 7HX | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/c9642c4f-ebb9-4ab9-8355-624c837ec5b8/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 63 | C70 | Batch 2 |  | Jalwinder Singh | 2026-02-27 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-27 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-02 |  | Programmed |  | H17S900 | Uploaded | 2026-03-05 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302957281 | 473278697710 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
10 Gorsey Bank Crescent Nantwich Cheshire | DW_00596_10 |  | CW5 7LX | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/6833e828-dd12-4f3c-8974-5f87e15f9186/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 63 | C72 | Batch 2 |  | Jalwinder Singh | 2026-03-04 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. | Evidence of damp or mould growth. | 2026-03-04 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-06 |  | Programmed |  | H18S400 | Uploaded | 2026-03-06 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302955547 | 473278697711 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Mould growth around bathroom window seals.
100 Main Road Crewe Cheshire | DW_00519_102 | Shavington | CW2 5DU | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/fb6aece3-b0a0-4843-b7f4-9ad98aa25e4e/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 62 | C74 | Batch 2 |  | Jalwinder Singh | 2026-02-26 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-26 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-03-02 |  | Programmed |  | B04S902 | Uploaded | 2026-03-05 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302955351 | 473378317540 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
7 Willow Crescent Crewe Cheshire | DW_00505_7 |  | CW2 8RL | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/a7e83906-83c7-494b-b974-89f21812e70b/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 62 | C75 | Batch 2 |  | Jalwinder Singh | 2026-02-26 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. | Evidence of damp or mould growth. | 2026-02-26 |  | V1 Uploaded | DMevs, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-02-27 |  | Programmed |  | B02S903 | Uploaded | 2026-02-27 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302955338 | 473291099347 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Very small amount of mould on some of the window seals in the property. Missing roof tile on rear elevation and moss growth on front elevation
7 School Lane Nantwich Cheshire | DW_00404_7 |  | CW5 5NQ | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/3e004cc9-a912-4c19-7ff1-08ddf03e139d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 62 | C75 | Batch 2 |  | Jalwinder Singh | 2026-03-02 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. | Evidence of damp or mould growth. | 2026-03-02 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-03 |  | Programmed |  | H13E900 | Uploaded | 2026-03-05 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302967814 | 473694046433 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Small amount of mould growth around BR2 window and around trickle vent. There is textured coating on LR, washing room, front door, BR1, BR2, BTH, WC & Landing ceilings. Could potentially contain asbestos. Customer has said that a neighbours property had a similar ceiling which was confirmed to have asbestos in it. Both openable windows in BR3 have missing locking mechanisms meaning they can’t be opened. Dropped eaves to first floor
45 Albion Street Crewe Cheshire | DW_00040_45 |  | CW2 8NG | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/b07b33e1-12ad-46da-a61f-956dd2659ed7/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 62 | C74 | Batch 2 |  | Jalwinder Singh | 2026-03-02 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. | Evidence of damp or mould growth. | 2026-03-02 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-03-06 |  | Programmed |  | B01S714 | Uploaded | 2026-03-06 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302973093 | 473418139892 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Mould growth visible on bedroom two ceiling. Unable to gain access to the loft due to obstruction by stored items.
102 Main Road Crewe Cheshire | DW_00519_100 | Shavington | CW2 5DU | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/0cbfb15c-888e-42cd-959b-032cf1ba0a72/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 61 | C75 | Batch 2 |  | Jalwinder Singh | 2026-02-26 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-02-26 |  | V1 Uploaded | DMevs, Solar PV, Loft insulation |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-03-02 |  | Programmed |  | B04S901 | Uploaded | 2026-03-05 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302951473 | 472653891774 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
20 Acton Road Crewe Cheshire | DW_00105_20 |  | CW2 8TN | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/ffba624d-6941-4559-a48f-bd65009a514e/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 61 | C73 | Batch 2 |  | Jalwinder Singh | 2026-03-02 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. | Evidence of damp or mould growth. | 2026-03-02 |  | V1 Uploaded | DMevs, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-03 |  | Programmed |  | H01S907 | Uploaded | 2026-03-05 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302967378 | 473258805441 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Mould visible on bedroom two upper window reveal due to cracked plaster. Wall and ceiling cracks visible in bedroom two and landing
18 Doddington Road Crewe Cheshire | DW_00077_18 |  | CW2 8ND | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/17d19a44-0b86-409a-9089-6ab2dbe455a6/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 61 | C72 | Batch 2 |  | Jalwinder Singh | 2026-03-04 | (V1) IOE/MTP Complete | 2.5KWP PV ARRAY SOUTH EAST. | Evidence of damp or mould growth. | 2026-03-04 |  | V1 Uploaded | DMevs, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-03-06 |  | Programmed |  | B01S915 | Uploaded | 2026-03-06 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302932708 | 473597615332 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Mould spores on bathroom ceiling.
7 Stanthorne Avenue Crewe Cheshire | DW_00078_7 |  | CW2 8NH | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/9ae05e96-3bc0-4e85-aac3-0c1b22677ede/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 61 | C74 | Batch 2 |  | Jalwinder Singh | 2026-03-04 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. | Evidence of damp or mould growth. | 2026-03-04 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-03-06 |  | Programmed |  | B01S716 | Uploaded | 2026-03-06 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302951505 | 473407281340 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Mould appearing on kitchen and bathroom ceiling and within other rooms.
6 Circle Avenue, Nantwich, Cheshire | DW_00510_6 |  | CW5 7HX |  |  | https://pashub.net/jobs/a36f5af0-61ad-4dcc-8b38-542bd6a62a7a/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 64 | C75 | Batch 2 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-03-16 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Requested |  | B13E900 | Uploaded | 2026-03-19 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315357644 | 492951418048 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed
4 Stanthorne Avenue, Crewe, Cheshire | DW_00078_4 |  | CW2 8NH | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/b0ba13a5-4d5a-4c49-9a18-a108f5af90e2/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | C78 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. | Evidence of damp or mould growth. | 2026-03-12 |  | V1 Uploaded | DMevs, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | H01S718 | Uploaded | 2026-03-17 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11315333702 | 492960380131 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed |  | mould appearing on ceiling and around windows, mould detected on walls. Roof tiles covered in moss.
270 Badger Avenue, Crewe, Cheshire | DW_00018_270 |  | CW1 3LW | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/8cbcb830-b036-4e7a-7ff0-08ddf03e139d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | B81 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. | Evidence of damp or mould growth. | 2026-03-13 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | H25S900 | Uploaded | 2026-03-17 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315358031 | 492962184404 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed |  | Mould growth around windows 3, 4, 5, 6, 9 & 10 and on ceiling of WC & BTH also on loft hatch as well as BR2 internal walls. Window 5’s outer pane has a crack in it. Major cracking to ceiling above front door which goes past the decorative layer, Cracks on ceiling on entirety of first floor in BR1, BR2, BR3, landing, BTH & staircase. Cracked tiles visible internally, although very difficult to evidence, Daylight visible in loft space, unsafe access into loft area and the majority of insulation being disturbed.
126 Claughton Avenue, Crewe, Cheshire | DW_00002_126 |  | CW2 6EY | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/3cf4a39e-1142-4d64-81ab-583bd9cc4337/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | C79 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. | Evidence of damp or mould growth. | 2026-03-13 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Programmed |  | H16M901 | Uploaded | 2026-03-17 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11315339712 | 493071409338 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed |  | Mould appearing around bed three window.
7 Dane Place, Crewe, Cheshire | DW_00256_7 |  | CW1 4SA | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/d52fed36-aac0-4ffc-b3a1-c5cca90509c5/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | B82 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-03-13 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Programmed |  | B10S901 | Uploaded | 2026-03-17 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11315333507 | 492962184406 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed
15 Dane Place, Crewe, Cheshire | DW_00256_15 |  | CW1 4SA | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/fe2b4677-dd48-4406-8d98-07778d46cade/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | B82 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. | Evidence of damp or mould growth. | 2026-03-13 |  | V1 Uploaded | DMevs, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Programmed |  | B10S902 | Uploaded | 2026-03-17 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11315320961 | 492960380130 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed |  | Mould appearing around windows mainly on silicon areas.
47 Rockwood Avenue, Crewe, Cheshire | DW_00006_47 |  | CW2 8LU | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/c54c548c-2bc1-4204-9726-bb73c36c5c17/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 67 | C79 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-03-12 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | H23E900 | Uploaded | 2026-03-17 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315340056 | 493117492473 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed
5 Skylark Close, Crewe, Cheshire | DW_00277_5 |  | CW1 3WE | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/65a2ed13-ed53-43d2-8036-08ddf03e139d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 67 | C77 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | Modelled PV 2KW |  | 2026-03-13 |  | V1 Uploaded | Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | H24E900 | Uploaded | 2026-03-17 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315318743 | 493004767450 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed |  | Damaged brick on front elevation.
8 Hazel Grove, Crewe, Cheshire | DW_00181_8 |  | CW1 4JL | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/4ff4d5a4-4cdf-4b1c-9690-35f101c3f38a/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 67 | C79 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-03-13 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Programmed |  |  | Uploaded | 2026-03-17 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315335831 | 492935230651 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed
14 Dane Place, Crewe, Cheshire | DW_00256_14 |  | CW1 4SA | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/5f8cb8d4-c5d6-4624-b104-dcd87dd5139b/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | B80 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-03-13 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Programmed |  | B10S900 | Uploaded | 2026-03-17 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315358040 | 493071409339 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed
2 Hurst Court, Tarporley, Cheshire | DW_00612_2 |  | CW6 9QX | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/eb3e7e4b-3bdb-43dd-8ba0-d8b706681242/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | C79 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-03-12 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Programmed |  | B08M900 | Uploaded | 2026-03-17 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315325534 | 493058827487 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed
5 Whitlow Avenue, Nantwich, Cheshire | DW_00420_5 |  | CW5 7BN | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/9f9e6a93-4e24-4f90-bf14-21b0d28e213f/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | C78 | Batch 3 |  | Jalwinder Singh | 2026-03-13 | (V1) IOE/MTP Complete | Modelled 2.KW | Evidence of damp or mould growth. | 2026-03-13 |  | V1 Uploaded | Solar PV, Loft insulation, DMevs |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | H26S900 | Uploaded | 2026-03-17 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315335978 | 491998871777 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed
59 Barons Road Crewe Cheshire | DW_00521_59 | Shavington | CW2 5ER | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/2f24a8ac-3d79-45b4-8566-59b5c05d40ef/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 59 | C71 | Batch 3 |  | Jalwinder Singh | 2026-03-05 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-03-05 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-03-04 |  | Programmed |  | B05S905 | Uploaded | 2026-03-10 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302951327 | 473697642713 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
7 Doddington Road Crewe Cheshire | DW_00077_7 |  | CW2 8ND | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/f3038d42-8f4b-45ba-b8c6-356ffb853f2a/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 59 | C70 | Batch 3 |  | Jalwinder Singh | 2026-03-05 | (V1) IOE/MTP Complete | 2.5 KWP PV ARRAY SOUTH EAST | Evidence of damp or mould growth. | 2026-03-05 |  | V1 Uploaded | DMevs, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-04 |  | Programmed |  | B01S717 | Uploaded | 2026-03-10 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302951348 | 473383802100 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Black mould spots spread across bathroom ceiling.
21 Coppice Road Nantwich Cheshire | DW_00514_21 |  | CW5 6QA | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/35bcb2fe-a57d-4f68-835e-8c99b1021345/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 58 | B82 | Batch 3 |  | Debbie Langer |  | (V1) IOE/MTP Complete | Property has SPV already installed, loft insulation is adequate, CWI is filled. HHRSH upgrade recommended to achieve C and duel immersion. |  | 2026-03-12 |  | V1 Uploaded | HHRSH |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | B07S900 | Uploaded | 2026-03-17 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302957395 | 473686791413 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
2 Weaver View Nantwich Cheshire | DW_00599_2 |  | CW5 6EB | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/1a02fb0e-44d5-4a67-a72c-3ad8900f80b2/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 58 | C70 | Batch 3 |  | Jalwinder Singh | 2026-03-06 | (V1) IOE/MTP Complete | 2.5 KWP PV ARRAY SOUTH EAST |  | 2026-03-06 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-04 |  | Programmed |  | H02M900 | Uploaded | 2026-03-10 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302934686 | 473376523506 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
16 Alvaston Walk Crewe Cheshire | DW_00097_16 |  | CW2 8PZ | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/eb651ec2-c1ce-44bb-bd73-621064557e00/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 57 | C72 | Batch 3 |  | Jalwinder Singh | 2026-03-06 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-03-06 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-03-04 |  | Programmed |  | B06M900 | Uploaded | 2026-03-10 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302957162 | 473298374855 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
43 Wistaston Green Road Crewe Cheshire | DW_00502_43 |  | CW2 8QX | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/21139721-1e4f-4288-9ab8-57d48e92d41f/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 57 | C74 | Batch 3 |  | Jalwinder Singh | 2026-03-06 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. |  | 2026-03-06 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  | 2026-03-04 |  | Programmed |  | B05S904 | Uploaded | 2026-03-10 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302951453 | 473400024294 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Moss build up on the front elevation off the roof.
38 Green Lane Nantwich Cheshire | DW_00511_38 |  | CW5 7JB | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/f622458c-3818-4952-9202-1e3ffec916b8/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 57 | C75 | Batch 3 |  | Jalwinder Singh | 2026-03-06 | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH EAST. | Evidence of damp or mould growth. | 2026-03-06 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-04 |  | Programmed |  | H04S902 | Uploaded | 2026-03-10 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302957397 | 473410890988 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Signs of possible leak in kitchen, Signs of moisture damage on bathroom ceiling. Mould growth around the window in bedroom 1. Also where the ceiling meets the rear wall. Mould around window area in bedroom 3, Cracks around window in front bedroom 2. 0mm loft insulation.
14 Tabley Road Crewe Cheshire | DW_00102_14 |  | CW2 8PW | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/5a4004bc-e316-478e-8d05-28a6a51df0c5/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 55 | C70 | Batch 3 |  | Debbie Langer | 2026-03-10 | (V1) IOE/MTP Complete | 2.0KW - Prefab house. Add Radbots on at least 2 Rads to ensure C score |  | 2026-03-10 |  | V1 Uploaded | Solar PV, Loft insulation | Radbots | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Programmed |  | H03S401 | Uploaded | 2026-03-13 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302955762 | 473695846604 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Signs of a possible water leak in the roof space of the kitchen. Tenant complain it had not been fixed
12 Atcherley Close Nantwich Cheshire | DW_00565_12 |  | CW5 8AW | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/7057f88f-458d-4fb7-8774-80d2cd7a1216/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 55 | C69 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2.5KWP PV ARRAY SOUTH. |  | 2026-03-11 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | H22E9000 | Uploaded | 2026-03-17 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302955692 | 473694046434 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
7 Festival Avenue Crewe Cheshire | DW_00588_7 |  | CW3 0DB | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/a6107fb0-45b2-4d10-747c-08ddf03a1f35/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 54 | C69 | Batch 3 |  | Debbie Langer | 2026-03-10 | (V1) IOE/MTP Complete | 2KW SE. Low starting Sap score. Added Hot water Cylinder insulation on as currently only 25mm. Change immersion to Duel also for 3 point increase |  | 2026-03-10 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV | Hotwater cylinder insulation | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Programmed |  | H02S901 | Uploaded | 2026-03-13 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302955173 | 472892711139 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
33 Cronkinson Avenue Nantwich Cheshire | DW_00424_33 |  | CW5 7BP | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/a6e75411-a393-4321-9c06-37b8742b4aa2/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 54 | C69 | Batch 3 |  | Debbie Langer | 2026-03-10 | (V1) IOE/MTP Complete | 2.5KW SE . Low starting Sap score. Added HWC jacket as current one falling off. | Evidence of damp or mould growth. | 2026-03-10 |  | V1 Uploaded | DMevs, Solar PV | Lels Hotwater cylinder insulation | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Programmed |  | H21S900 | Uploaded | 2026-03-13 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302951328 | 473690452176 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Seal has gone in some windows, condensation visible- On one of the purlins there is Significant discolouration, potentially mould.
2 Weaver Road Nantwich Cheshire | DW_00403_2 |  | CW5 5NJ | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/629c0496-07b6-4847-a2df-08ddffed72a4/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 54 | C69 | Batch 3 |  | Debbie Langer | 2026-03-13 | (V1) IOE/MTP Complete | 2.5 KW SE- If property has less PV than this - property would nee Radbots also. Low starting score |  | 2026-03-10 |  | V1 Uploaded | Solar PV, Loft insulation | Lels | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Programmed |  | H20E900 | Uploaded | 2026-03-13 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302951351 | 473599439082 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
6 Mere Close, Crewe, Cheshire | DW_00550_6 |  | CW1 5PR | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/029a2cbe-4539-40aa-869c-6a1a17e5bf25/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 63 | C80 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-03-17 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Requested |  | B05M900 | Uploaded | 2026-03-19 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315359365 | 492915468518 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed
3 Mere Close, Crewe, Cheshire | DW_00550_3 |  | CW1 5PR | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/1f9cc11e-08b4-4a95-893b-d4e55ee2127a/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 63 | C77 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. | Evidence of damp or mould growth. | 2026-03-17 |  | V1 Uploaded | DMevs, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Requested |  | B05S906 | Uploaded | 2026-03-19 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11315345679 | 493131872486 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed |  | Slight mould growth around bed 1 window on silicone Moss / vegetation on roof.
49 Plane Tree Drive, Crewe, Cheshire | DW_00068_49 |  | CW1 4ET | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/5aff2995-8dc6-4fd5-83a8-7e89d24314dd/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 62 | C73 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2.5KWP PV ARRAY SOUTH. |  | 2026-03-18 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Requested |  | H28S800 | Uploaded | 2026-03-19 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315328506 | 492992204009 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed
5 Crosslands, Crewe, Cheshire | DW_00552_5 |  | CW1 5TG | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/88a93145-582f-4f83-9e65-acc084399994/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 62 | C76 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-03-18 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Requested |  | B05S907 | Uploaded | 2026-03-19 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11315320836 | 492039494875 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed |  | Two broken roof tiles on rear roof
40 Abbey Place, Crewe, Cheshire | DW_00251_40 |  | CW1 4JR | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/a3c4ffff-63b1-4c88-9d6f-641f97099f34/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | C79 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KW SE Debbie to check if extension has been added on at later date. - Main build date also wrong should be later 60-70s- will need changing at Post EPR stage |  | 2026-03-16 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Requested |  | H27M900 | Uploaded | 2026-03-19 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315357818 | 492988622014 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed
13 Dane Place, Crewe, Cheshire | DW_00256_13 |  | CW1 4SA | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/03e0950f-d890-44bc-b2c8-f409b9785075/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 65 | C79 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. | Evidence of damp or mould growth. | 2026-03-16 |  | V1 Uploaded | DMevs, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Requested |  | B10E900 | Uploaded | 2026-03-19 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315334681 | 493119290558 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed |  | Mould/damp appearing on bathroom ceiling.
34 Acton Road, Crewe, Cheshire | DW_00105_34 |  | CW2 8TN | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/1656005e-69e5-4993-b676-7b22b64e8301/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 64 | C75 | Batch 3 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-03-16 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Requested |  | H01S909 | Uploaded | 2026-03-19 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315333847 | 492988622015 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed |  | Roof condition considered to be poor internally roof felt none existent.
29 Greenacres, Crewe, Cheshire | DW_00255_29 |  | CW1 4JU | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/d54378b2-1f21-4b50-975f-c56c4bdfc2e6/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 63 | C78 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KW PV SOUTH |  | 2026-03-20 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  | 2026-03-25 |  |  | Programmed |  | H33E900 | Uploaded | 2026-03-25 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315333645 | 493115697374 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed
50 Greenacres, Crewe, Cheshire | DW_00255_50 |  | CW1 4JU | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/51f3820f-ba71-4945-83c0-e5d770c09403/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | C77 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KW Solar SE |  | 2026-03-20 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  | 2026-03-25 |  |  | Programmed |  | H27M901 | Uploaded | 2026-03-25 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11315345526 | 492821386442 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed
155 Remer Street, Crewe, Cheshire | DW_00066_155 |  | CW1 4LZ | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/1c06198e-d9a0-405a-8293-a098e65c6dcc/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 63 | C73 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. | Evidence of damp or mould growth. | 2026-03-18 |  | V1 Uploaded | DMevs, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  | 2026-03-25 |  |  | Programmed |  | H30E700 | Uploaded | 2026-03-20 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315325721 | 492963972325 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed |  | Some evidence of mould build up around silicon window seals. Damp and mould also visible within the property.
10 Henry Street, Crewe, Cheshire | DW_00238_10 |  | CW1 4BH | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/9f11e66e-39f0-4f06-266f-08ddf038716d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 63 | C79 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-03-26 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  | 2026-03-25 |  |  | Programmed |  | B14E900 | Uploaded | 2026-03-20 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315333569 | 493080407238 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed |  | Cracks / Pointing defects on rear elevation of the property. There are some missing tiles and some on the front elevation.
153 Remer Street, Crewe, Cheshire | DW_00066_153 |  | CW1 4LZ | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/b99380ed-9798-4c3a-9eec-25b273411b6f/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 63 | C89 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2.5 KW Solar PV - MTP updated as ASHP was selected in the IOE. |  | 2026-03-26 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  | 2026-03-25 |  |  | Programmed |  | H31E700 | Uploaded | 2026-03-20 | B | Archetype (Simple) | Design A completed | [30 empty] | 11315325611 | 493075006665 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed
8 Volunteer Avenue, Nantwich, Cheshire | DW_00417_8 |  | CW5 5PR | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/c25ae43f-d0d0-46f0-2511-08ddf038716d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 62 | C72 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. | Evidence of damp or mould growth. | 2026-03-18 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  | 2026-03-25 |  |  | Programmed |  | H32S800 | Uploaded | 2026-03-20 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315340059 | 493069607105 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed |  | Double glazing has a mixture of issues. Window 4 in the hallway has a crack on the inner pane, window 10 in BR1 is missing its handle and windows 1, 2 and 3 in LR/DR and window 14 in both have mould growth on and around them as well as the ceiling.
5 Mere Close, Crewe, Cheshire | DW_00550_5 |  | CW1 5PR | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/4c84f9b9-6248-4a6d-bc1d-703e14a56f28/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 62 | C77 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-03-19 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  | 2026-03-25 |  |  | Programmed |  | B05S909 | Uploaded | 2026-03-20 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315317023 | 492016027897 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed
107 Claughton Avenue, Crewe, Cheshire | DW_00002_107 |  | CW2 6ET | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/bcab4209-69f8-483b-9978-18d30dc5e5bf/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 61 | C75 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KW PV SOUTH. | Evidence of damp or mould growth. | 2026-03-24 |  | V1 Uploaded | DMevs, CWI, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  | 2026-03-25 |  |  | Programmed |  | H08E902 | Uploaded | 2026-03-25 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315328682 | 492016027896 | Joseph Westwood Feb 19, 2026 2:56 PM |  |  | Bathroom ceiling shows signifcant damage, with peeling paint and cracked plaster exposing the surface underneath, which may indicate past moisture issues.
41 Wistaston Green Road, Crewe, Cheshire | DW_00502_41 |  | CW2 8QX | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/f24d019c-9e69-4891-99fb-5bfa44bce049/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 61 | C77 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-03-19 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  | 2026-03-25 |  |  | Programmed |  | B15E900 | Uploaded | 2026-03-25 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315326325 | 491993552107 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed
21 Edwards Avenue Crewe Cheshire | DW_00517_21 | Shavington | CW2 5BT | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/e29b2917-29a0-48a0-800c-3934a4267401/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 60 | C69 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2.5 KWP PV ARRAY SOUTH. | Evidence of damp or mould growth. | 2026-03-19 |  | V1 Uploaded | DMevs, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  | 2026-03-25 |  |  | Programmed |  | H15S902 | Uploaded | 2026-03-20 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302957466 | 473525659877 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Extension has severe black mould present. Unable to record moisture meter reading to due ceiling material.
9 Crosslands, Haslington | DW_00552_9 |  | CW1 5TG | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/5848e31a-f0eb-46e4-9dde-e06ce873e8f9/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 60 | C75 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-03-19 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  | 2026-03-25 |  |  | Programmed |  | B05S908 | Uploaded | 2026-03-20 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11315334141 | 492823202026 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed |  | On the rear elevation there are a number of missing and moved roof tiles
144 Lime Tree Avenue, Crewe, Cheshire | DW_00055_144 |  | CW1 4HY | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/3ad81ac6-d904-422e-bb9a-27743a08c739/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 60 | C71 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KW SE |  | 2026-03-26 |  |  | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | H30S700 | Uploaded | 2026-03-27 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315339536 | 493124674768 | Joseph Westwood Feb 19, 2026 2:56 PM
9 Mere Close, Crewe, Cheshire | DW_00550_9 |  | CW1 5PR | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/dda3caa1-cf09-4294-81de-1926f76afd15/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 60 | C75 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-03-25 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | B05M901 | Uploaded | 2026-03-26 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315316615 | 493075006666 | Joseph Westwood Feb 19, 2026 2:56 PM
44 Barthomley Crescent, Crewe, Cheshire | DW_00110_44 |  | CW2 8TP | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/0db50760-4df8-4437-9642-b4802ab1464f/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 59 | C73 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2.5 KWP PV ARRAY SOUTH. | Evidence of damp or mould growth. | 2026-03-24 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | B01S900 | Uploaded | 2026-03-25 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315345680 | 492048517369 | Joseph Westwood Feb 19, 2026 2:56 PM |  |  | Mould appearing around bedroom 2 window and on bathroom ceiling.
18 Oakfield Close, Wrenbury | DW_00573_18 |  | CW5 8ET | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/ff6bf5ac-d5fe-4b13-a705-45573735c20e/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 59 | C75 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KW PV SOUTH. |  | 2026-03-25 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | B04S901 | Uploaded | 2026-03-25 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11315319306 | 492052083924 | Joseph Westwood Feb 19, 2026 2:56 PM |  |  | The loft hatch is broken and it could not be opened. New door to be fitted. Significant amount of moss growth on the rear elevation and some of the tiles are lifting, Pointing deteriorating rear elevation.
77A Crewe Road, Crewe, Cheshire | DW_00547_77A |  | CW1 5QX | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/9255a784-a5fb-44cc-8f6b-ebdb2f6b1ebb/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 59 | C75 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KW PV SOUTH. |  | 2026-03-25 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | B16E900 | Uploaded | 2026-03-26 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315357821 | 492108905680 | Joseph Westwood Feb 19, 2026 2:56 PM
3 Roedean Walk, Crewe, Cheshire | DW_00253_3 |  | CW1 4LG | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/a7e9f52b-f87f-4705-8152-dbe153d0cf3d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 59 | C72 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2.5KWP PV ARRAY SOUTH. |  | 2026-03-25 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Programmed |  | H21M900 | Uploaded | 2026-03-26 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315328543 | 493119290557 | Joseph Westwood Feb 19, 2026 2:56 PM
14 Somerford Avenue Crewe Cheshire | DW_00079_14 |  | CW2 8NE | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/f5b20f77-dbdc-45fc-bc88-a7c063d4d167/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 59 | C73 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2.5KWP PV ARRAY SOUTH. |  | 2026-03-26 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Programmed |  | B01S720 | Uploaded | 2026-03-26 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302934504 | 473278697706 | Joseph Westwood Feb 18, 2026 12:10 PM
167 Remer Street, Crewe, Cheshire | DW_00066_167 |  | CW1 4LZ | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/e09137e0-0d1a-4f37-ae3e-e6aae2188630/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | C76 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | RA has stated that the property is a system build / solid wall construction- Pibi needed to confirm wall type as looks like solid with render | Evidence of damp or mould growth. | 2026-03-16 |  | V1 Uploaded | DMevs, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  | 2026-03-25 |  |  | Programmed |  | H03S700 | Uploaded | 2026-03-20 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11315357795 | 492999401714 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed |  | Rising damp - Damp present in the bathroom, moisture reading 15.6%. Bed 1 and bed 2.
17 Sherborne Road, Crewe, Cheshire | DW_00250_17 |  | CW1 4LA | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/c2835ab9-2c39-40f7-a0a1-2c18e1e925c8/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 65 | C77 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KW Debbie to check if extension has been added on at later date. Odd one. |  | 2026-03-16 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  | 2026-03-25 |  |  | Programmed |  | H20M900 | Uploaded | 2026-03-20 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315358397 | 492997605620 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed
67 Coronation Street, Crewe, Cheshire | DW_00075_67 |  | CW1 4EE | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/1433a2f4-ff3d-4bd4-266e-08ddf038716d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 64 | C78 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. |  | 2026-03-17 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  | 2026-03-25 |  |  | Programmed |  | B12S900 | Uploaded | 2026-03-20 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11315358037 | 492048518330 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed |  | There is a crack on bathroom wall.
10 Darley Avenue Crewe Cheshire | DW_00080_10 |  | CW2 8NF | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/59f0cae5-d1bd-4db2-9411-93c4fd925c45/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 59 | C73 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2.5KWP PV ARRAY SOUTH. |  | 2026-03-26 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Programmed |  | B01S719 | Uploaded | 2026-03-26 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302954977 | 473695846605 | Joseph Westwood Feb 18, 2026 12:10 PM
193 Lime Tree Avenue, Crewe, Cheshire | DW_00055_193 |  | CW1 4HZ | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/df71cf83-fb45-481f-9bc0-b58fb51c645d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 58 | C70 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2.5KWP PV ARRAY SOUTH. |  | 2026-03-27 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | H28S701 | Uploaded | 2026-03-27 | A | [32 empty] | 11315358200 | 493126473963 | Joseph Westwood Feb 19, 2026 2:56 PM
1 St Marys Road, Nantwich, Cheshire | DW_00407_1 |  | CW5 5NU | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/2cdaaca5-571e-48a7-0087-08ddf03803e1/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 57 | C71 | Batch 4 |  | Debbie Langer |  | (V1) IOE/MTP Complete | 2.5KE SE - not modelled CWI in extension due to age, assumed already got some built in. Main house is Solid- build date is correct | Evidence of damp or mould growth. | 2026-03-27 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Requested |  | H38S900 | To review | [34 empty] | 11315326517 | 493066015960 | Joseph Westwood Feb 19, 2026 2:56 PM |  |  | Dropped eaves to first floor, mould growth in numerous places in whole of house & Bathroom. The main house pitched roof has some visible damage to the tiling.
32 Marple Crescent Crewe Cheshire | DW_00101_32 |  | CW2 8PP | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/69a107c5-1792-4b55-96b8-ab756970af12/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 57 | C71 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2.5KWP PV ARRAY SOUTH. |  | 2026-03-26 |  | V1 Uploaded | Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | H02S400 | Uploaded | 2026-03-27 | A | [32 empty] | 11302955123 | 473298374854 | Joseph Westwood Feb 18, 2026 12:10 PM
34 Doddington Road Crewe Cheshire | DW_00077_34 |  | CW2 8NQ | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/40071b2d-5f41-4db4-af88-b5d9cca1d60b/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 57 | C69 | Batch 4 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2.5KW PV SOUTH. Low starting Sap score. Added Hot water Cylinder insulation on as currently only 25mm & LELs. Just about achieved a C. | Evidence of damp or mould growth. | 2026-03-26 |  | V1 Uploaded | DMevs, Solar PV | Lels Hotwater cylinder insulation | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | B01S721 | Uploaded | 2026-03-27 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302943199 | 473291099349 | Joseph Westwood Feb 18, 2026 12:10 PM |  |  | Significant amount of mould and damp visible at multiple locations within the property.
6 White Avenue, Crewe, Cheshire | DW_00013_6 |  | CW2 7SH | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/ea60a30e-37b1-431d-a7ff-e2c13e58f196/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 56 | C69 | Batch 4 |  | Debbie Langer |  | (V1) IOE/MTP Complete | 2.5KW PV SE | Evidence of damp or mould growth. | 2026-03-23 |  | V1 Uploaded | DMevs, Heating controls, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  | 2026-03-25 |  |  | Programmed |  | H02S700 | Uploaded | 2026-03-25 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11315339859 | 493031761082 | Joseph Westwood Feb 19, 2026 2:56 PM |  |  | Bathroom ceiling is covered in light mould spots
22 Tabley Road Crewe Cheshire | DW_00102_22 |  | CW2 8PW | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/46f65966-0519-4766-ae99-6026c6121677/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 56 | C71 | Batch 4 |  | Debbie Langer |  | (V1) IOE/MTP Complete | 3KW SE Should this be on the EWI programme? |  | 2026-03-23 |  | V1 Uploaded | Solar PV | Lels | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  | 2026-03-25 |  |  | Programmed |  | H03S402 | Uploaded | 2026-03-25 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302957226 | 473387396330 | Joseph Westwood Feb 18, 2026 12:10 PM
36 Barons Road Crewe Cheshire | DW_00521_36 | Shavington | CW2 5ER | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/761defaa-e412-4227-8941-6a315566139c/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 53 | C73 | Batch 4 |  | Debbie Langer |  | (V1) IOE/MTP Complete | 2.0 KW PV HHRSH to replace current heaters | Evidence of damp or mould growth. | 2026-03-23 |  | V1 Uploaded | DMevs, Solar PV, HHRSH |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  | 2026-03-25 |  |  | Programmed |  | B05S910 | Uploaded | 2026-03-24 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302955063 | 473595810020 | Joseph Westwood Feb 18, 2026 12:10 PM |  |  | Mould growth visible around bedroom one window
4 Chorley Green Nantwich Cheshire | DW_00535_4 |  | CW5 8JR | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/7e3172cf-f737-479b-848b-8efc65832c69/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 56 | C69 | Batch 4 |  | Debbie Langer |  | (V1) IOE/MTP Complete | 2.5KW Solar PV at least to to achieve C. Old ASHP could do with Replacing |  | 2026-03-23 |  | V1 Uploaded | DMevs, Solar PV, Loft insulation | Lels | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  | 2026-03-25 |  |  | Programmed |  | H34S900 | Uploaded | 2026-03-26 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302951167 | 473593933023 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
23 Cronkinson Avenue Nantwich Cheshire | DW_00424_23 |  | CW5 7BP |  |  | https://pashub.net/jobs/82c0e1e0-93f4-4d4e-b4e6-d41a5330b437/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 56 | C71 | Batch 5 |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | 2KWP PV ARRAY SOUTH. | Evidence of damp or mould growth. | 2026-03-30 |  | V1 Uploaded | DMevs, Loft insulation, CWI, Solar PV | [12 empty] | Requested |  |  | Instructed | [34 empty] | 11302934730 | 473597615331 | Joseph Westwood Feb 18, 2026 12:10 PM |  |  | Mould/damp visible around front external Windows.
25 Marple Crescent Crewe Cheshire | DW_00101_25 |  | CW2 8PP |  |  | https://pashub.net/jobs/3277b32c-fb48-404a-8e71-0192530c4e6d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 55 |  | Batch 5 |  | Jalwinder Singh |  | RA issue | RA has stated the property is to be cavity, system build and solid, evidence of cavity filled borescope survey | [20 empty] | Outstanding | [34 empty] | 11302967236 | 473690375359 | Joseph Westwood Feb 18, 2026 12:10 PM
24 Cronkinson Avenue Nantwich Cheshire | DW_00424_24 |  | CW5 7BP |  |  | https://pashub.net/jobs/83e7be10-da07-432f-9163-363b001f4e9d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 55 |  | Batch 5 |  | Jalwinder Singh |  | RA issue | RA has stated that the property construction is solid brick, but photos show evidence of cavity filled. | [20 empty] | Outstanding | [34 empty] | 11302943591 | 473282284753 | Joseph Westwood Feb 18, 2026 12:10 PM
18 Hillfield Gardens Nantwich Cheshire | DW_00411_18 |  | CW5 7BU |  |  | https://pashub.net/jobs/0a734fdc-736d-4b18-a35c-55b78a4a3418/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 55 |  | Batch 5 |  | Jalwinder Singh |  | RA issue | RA has stated that the property construction is solid brick, but photos show evidence of cavity filled borescope survey | [20 empty] | Outstanding | [34 empty] | 11302966540 | 473694046436 | Joseph Westwood Feb 18, 2026 12:10 PM
113 Marshfield Avenue Crewe Cheshire | DW_00111_113 |  | CW2 8TE |  |  | https://pashub.net/jobs/2b959a8c-51e5-40d8-9dd3-53beff44aeba/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 53 |  | Batch 5 |  | Jalwinder Singh |  | RA issue | RA has stated that the property is solid wall but photos show its cavity filled. RA has also stated that the property is CWI evidence of borescope survey. | [20 empty] | Outstanding | [34 empty] | 11302951411 | 473593933021 | Joseph Westwood Feb 18, 2026 12:10 PM |  |  | Felt in loft space is torn away from rafters exposing the roof tiles.
287 Cobbs Lane Nantwich Cheshire | DW_00558_287 |  | CW5 7NT |  |  | https://pashub.net/jobs/243bdb1d-8778-4d56-81af-330421767a55/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 52 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11302951733 | 473387396332 | Joseph Westwood Feb 18, 2026 12:10 PM |  |  | Cracks visible on the ceiling in bed 1.
10 Doddington Road Crewe Cheshire | DW_00077_10 |  | CW2 8ND |  |  | https://pashub.net/jobs/44683795-adce-41c0-9c66-a4b2d9036878/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 52 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11302968164 | 473258805442 | Joseph Westwood Feb 18, 2026 12:10 PM
213 Lime Tree Avenue, Crewe, Cheshire | DW_00055_213 |  | CW1 4HZ |  |  | https://pashub.net/jobs/61eb8f5c-fd81-4390-b1d4-67bbaa5cf52b/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 52 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315316614 | 492094529769 | Joseph Westwood Feb 19, 2026 2:56 PM
12 Stanthorne Avenue Crewe Cheshire | DW_00078_12 |  | CW2 8NH |  |  | https://pashub.net/jobs/d963bc60-13e1-49e1-95c9-a7f5c0ef0fa9/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 51 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11302953943 | 473601228996 | Joseph Westwood Feb 18, 2026 12:10 PM
6 Atcherley Close, Nantwich, Cheshire | DW_00565_6 |  | CW5 8AW |  |  | https://pashub.net/jobs/4f53a26e-c0fb-460a-8824-50767c3f6965/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 51 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315357350 | 493124674769 | Joseph Westwood Feb 19, 2026 2:56 PM
14 Stanthorne Avenue, Crewe, Cheshire | DW_00078_14 |  | CW2 8NH |  |  | https://pashub.net/jobs/b2a1749f-6167-427c-a93e-bc02fc218a0a/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 51 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315333575 | 492956783804 | Joseph Westwood Feb 19, 2026 2:56 PM
14 Weaver View Nantwich Cheshire | DW_00599_14 |  | CW5 6EB |  |  | https://pashub.net/jobs/bd29ce85-2815-41f1-9442-e922da6bed67/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 50 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11302951594 | 473378317542 | Joseph Westwood Feb 18, 2026 12:10 PM
40 Doddington Road, Crewe, Cheshire | DW_00077_40 |  | CW2 8NQ |  |  | https://pashub.net/jobs/ab83bb5e-a873-4177-9743-cfe5bc0a383d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 50 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315320825 | 493024558270 | Joseph Westwood Feb 19, 2026 2:56 PM
45 Wilbraham Road Nantwich Cheshire | DW_00540_45 |  | CW5 8LQ |  |  | https://pashub.net/jobs/d77cd328-1cdb-4d89-935d-e6f915786144/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 49 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11302955064 | 473690375362 | Joseph Westwood Feb 18, 2026 12:10 PM
13 Stanthorne Avenue Crewe Cheshire | DW_00078_13 |  | CW2 8NH |  |  | https://pashub.net/jobs/3d775072-e8d0-4805-80bb-3e5221d7f89b/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 46 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11302957254 | 473376523505 | Joseph Westwood Feb 18, 2026 12:10 PM
1 Lightwood Green Avenue Crewe Cheshire | DW_00580_1 |  | CW3 0EN |  |  | https://pashub.net/jobs/0527bab3-46c0-44df-74fd-08ddf03a1f35/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 45 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11302951487 | 473593995451 | Joseph Westwood Feb 18, 2026 12:10 PM
1 Atcherley Close Nantwich Cheshire | DW_00565_1 |  | CW5 8AW |  |  | https://pashub.net/jobs/06ef13d2-0797-471c-9bf1-98e02d77797b/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 45 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11302934685 | 473400024295 | Joseph Westwood Feb 18, 2026 12:10 PM
22 Alvaston Walk Crewe Cheshire | DW_00097_22 |  | CW2 8PZ |  |  | https://pashub.net/jobs/44683795-adce-41c0-9c66-a4b2d9036878/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 45 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11302953515 | 473608458472 | Joseph Westwood Feb 18, 2026 12:10 PM
47 Albion Street Crewe Cheshire | DW_00040_47 |  | CW2 8NG |  |  | https://pashub.net/jobs/c06eab0e-92ec-4e8e-9174-42e0742cdff3/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 45 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11302955760 | 473595810021 | Joseph Westwood Feb 18, 2026 12:10 PM
1 Oakfield Close, Nantwich, Cheshire | DW_00573_1 |  | CW5 8ET |  |  | https://pashub.net/jobs/1e74c982-f08d-4160-b730-d11754d3ed85/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 45 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315335979 | 492693466326 | Joseph Westwood Feb 19, 2026 2:56 PM
27 Wilbraham Road, Nantwich, Cheshire | DW_00540_27 |  | CW5 8LQ |  |  | https://pashub.net/jobs/dc5eb7eb-5410-48eb-9ab0-3367d065e2ed/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 45 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315335539 | 493013769427 | Joseph Westwood Feb 19, 2026 2:56 PM
3 Mill Pool Cottages Mill Pool Lane Nantwich | DW_00542_3 |  | CW5 6AU |  |  | https://pashub.net/jobs/16c37b11-2681-43a7-7eea-08ddf03e139d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 43 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11302951452 | 473383802102 | Joseph Westwood Feb 18, 2026 12:10 PM
49 Wistaston Green Road Crewe Cheshire | DW_00502_49 |  | CW2 8QX |  |  | https://pashub.net/jobs/0de01973-aee7-4d0d-a15b-e754ac277f04/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 43 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11302968161 | 473593933022 | Joseph Westwood Feb 18, 2026 12:10 PM
33 Wilbraham Road, Nantwich, Cheshire | DW_00540_33 |  | CW5 8LQ |  |  | https://pashub.net/jobs/eb9cc200-d67a-4038-a84f-e4e2a6d65860/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 42 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315319265 | 492953213159 | Joseph Westwood Feb 19, 2026 2:56 PM
1 Crowton Cottages, Winsford, Road, Winsford, Cheshire | DW_00536_1 |  | CW7 4DP |  |  | https://pashub.net/jobs/271f43c3-7246-41df-ae65-ade8bc2bd777/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 40 |  | Batch 5 |  | Jalwinder Singh |  | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315326274 | 492935230650 | Joseph Westwood Feb 19, 2026 2:56 PM
3 Sherborne Road, Crewe, Cheshire | DW_00250_3 |  | CW1 4LA |  |  | https://pashub.net/jobs/190f9673-600c-4303-b319-f154f472b33e/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 55 | C69 | Batch 5 | Hubspot view | Debbie Langer |  | (V1) IOE/MTP Complete | 2.5KW PV- processed through Hubspot |  | 2026-03-24 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV | Radbots | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Programmed |  | H36M900 | Uploaded | 2026-03-26 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315358201 | 492962184405 | Joseph Westwood Feb 19, 2026 2:56 PM |  |  | Mould growth around the window in bedroom 1 and Large cracks along the top of the internal party wall with bathroom and internal party wall with bedroom 2
15 Edwards Close Crewe Cheshire | DW_00518_15 | Shavington | CW2 5BU |  |  | https://pashub.net/jobs/b743f3d9-251a-477d-9042-f509444c2773/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 53 | C70 | Batch 5 | Hubspot view | Debbie Langer |  | (V1) IOE/MTP Complete | 2.5 KW SE |  | 2026-03-26 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [10 empty] | Requested |  | B02S904 | To review | [34 empty] | 11302940560 | 472892711140 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Signs of damp visible below window in bedroom one
5 Festival Avenue Crewe Cheshire | DW_00588_5 |  | CW3 0DB |  |  | https://pashub.net/jobs/c1109f01-84e4-4228-7e79-08ddf03e139d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 40 | B81 | Batch 5 |  | Saskia Ratcliff |  | (V1) IOE/MTP Complete | PV 3.48kw SOUTH - plus loft (300mm) and Dmevs only achieves D56 as LPG bottled gas boiler in situ - will need ASHP install with 3kw south =B81 | Evidence of damp or mould growth. | 2026-03-24 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV, ASHP |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Requested |  | H37S900 | Uploaded | 2026-03-27 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302951349 | 473278697708 | Joseph Westwood Feb 18, 2026 12:10 PM |  |  | Mould growth around living room front window and upstairs landing window. On the bathroom and bedroom 2 ceiling and relatively large amount of condensation mould around bedroom 1 window and on ceiling
18 Chapel Close, Winsford, Cheshire | DW_00537_18 |  | CW7 4DT |  |  | https://pashub.net/jobs/d0bd924d-61a3-411c-8a86-d8c1caee1e04/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 40 | C72 | Batch 5 |  | Saskia Ratcliff |  | (V1) IOE/MTP Complete | RA input error - boiler PCDB is correct but photo evidence shows fuel is not BULK LPG but bottled - changes pre E to F but may not need changing as will need ASHP install , Dmevs, PV, and Loft (300mm to main only) |  | 2026-03-25 |  | V1 Uploaded | ASHP, Loft insulation, Solar PV, DMevs |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Requested |  | H39S900 | Work in progress | [34 empty] | 11315328206 | 493010168001 | Joseph Westwood Feb 19, 2026 2:56 PM
16 Festival Avenue Crewe Cheshire | DW_00588_16 |  | CW3 0DB |  |  | https://pashub.net/jobs/5b58c564-905b-4def-7e76-08ddf03e139d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 39 | B81 | Batch 5 |  | Saskia Ratcliff |  | (V1) IOE/MTP Complete | PV 3.48kw WEST - plus loft (300mm) and Dmevs only achieves E53 as LPG bottled gas boiler in situ with 3.48kw WEST =B81 (3KW WEST =C79) |  | 2026-03-24 |  | V1 Uploaded | ASHP, DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [10 empty] | Requested |  |  | Instructed | [34 empty] | 11302957465 | 473282284754 | Joseph Westwood Feb 18, 2026 12:10 PM
2 Woodford Close Crewe Cheshire | DW_00092_2 |  | CW2 8QN | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/0ff977f5-23c5-4582-8321-a83bae516d8d/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 58 | C74 | EWI BATCH |  | Debbie Langer |  | (V2) IOE/MTP Complete | Planned EWI install, EWI and Loft only achieve D64 - would still require PV. 2KW modelled | Evidence of damp or mould growth. | 2026-03-12 |  | V2 Uploaded | DMevs, Loft insulation, Solar PV, EWI |  | V2 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-03-04 | EWI, NEEDS REVISION | Programmed |  | H19S900 | Stuck | 2026-03-10 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302955460 | 473595810022 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed | KN | Roof felt is in poor condition. Mould growth around windows in living room and bedroom 2.
69 Tatton Road Crewe Cheshire | DW_00090_69 |  | CW2 8PX | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/86ee2faa-dd99-4e1e-8157-5e10237914ff/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 57 | C70 | EWI BATCH |  | Debbie Langer | 2026-02-26 | (V2) IOE/MTP Complete | Planned EWI install, Ioe was incorrect- this will need new pre EPR uploading to show as built. Score with EWI would be D62- so would still need Solar to achieve C | Evidence of damp or mould growth. | 2026-03-12 |  | V2 Uploaded | DMevs, Solar PV, EWI |  | V2 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-02-27 |  | Programmed |  | H05M700 | Uploaded | 2026-02-27 | B | Archetype (Simple) | Design A completed | [30 empty] | 11302955759 | 473690452174 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed | KN | Evidence of mould growth on the seals of some of the windows. In the bathroom there is mould growth on the window frames and around the window reveals also some on the bathroom ceiling. Has had issues with mould in B1 coming up from skirting boards. Has been told wall isn’t damp. No evidence recently as been treated.
43 Ash Road, Crewe, Cheshire | DW_00058_43 |  | CW1 4DU | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/dae9fe00-b314-4a3d-01e5-08ddf03803e1/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | C69 | EWI BATCH |  | Jalwinder Singh |  | (V1) IOE/MTP Complete | EWI needs remodelling 2.5KW Starting Sap rate should be D65 Incorrect wall type, should be Cavity Wall filled. | Evidence of damp or mould growth. | 2026-03-13 |  | V1 Uploaded | Solar PV, DMevs |  | V1 Confirmed for invoicing | [5 empty] | Juan Gonzalez |  |  |  |  | Programmed |  | H26S700 | Uploaded | 2026-03-17 | A | Archetype (Simple) | Design A completed | [30 empty] | 11315333700 | 492963972326 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed | KN | Crack to roof overhang on rear elevation. Condensation on outside of LR2 window , mould growth on ceiling & walls of BR2 bay window & around seal of window 8. Textured coating to WC ceiling. Could potentially contain asbestos. Dropped eaves to first floor.
48 Moreton Road Crewe Cheshire | DW_00085_48 |  | CW2 8QT | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/36c97408-8207-4820-bd91-025c8cd30f5f/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 58 | C72 | EWI BATCH |  | Debbie Langer |  | (V1) IOE/MTP Complete | EWI needed |  | 2026-03-23 |  | V1 Uploaded | DMevs, EWI, Windows |  | V1 Confirmed for invoicing | [10 empty] | Requested |  |  | Instructed | [34 empty] | 11302934689 | 472653891777 | Joseph Westwood Feb 18, 2026 12:10 PM |  | KN
33 Tatton Road, Crewe, Cheshire | DW_00090_33 |  | CW2 8QA | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/484c9fd3-5462-43bf-a1fe-582aba994818/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 62 | C71 | EWI BATCH |  | Debbie Langer |  | (V1) IOE/MTP Complete | Planned EWI install, please review IOE |  | 2026-03-12 |  | V1 Uploaded | DMevs, EWI, Loft insulation |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  | EWI to System Built | Programmed |  | EWI | To review |  | A | Archetype (Complex) | [31 empty] | 11315326324 | 492990421225 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed | KN
44 Tatton Road, Crewe, Cheshire | DW_00090_44 |  | CW2 8QA | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/d41a77d4-deb3-4980-910f-0c770f10f8d0/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 62 | C73 | EWI BATCH |  | Debbie Langer |  | (V1) IOE/MTP Complete | Planned EWI install, |  | 2026-03-12 |  | V1 Uploaded | DMevs, EWI |  | V1 Confirmed for invoicing | [10 empty] | Programmed |  | EWI | Stuck | [34 empty] | 11315325746 | 493124674767 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed | KN
7 Aldersey Road, Crewe, Cheshire | DW_00084_7 |  | CW2 8NPsl | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/d089cd13-70dd-4392-b4f2-6a0943bdabbd/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 58 | C74 | EWI BATCH |  | Debbie Langer |  | (V1) IOE/MTP Complete | Planned EWI install, EWI alone would not reach C. Solar modelled at 2.0KW also |  | 2026-03-12 |  | V1 Uploaded | DMevs, EWI, Solar PV |  | V1 Confirmed for invoicing | [9 empty] | EWI | Programmed |  | EWI | Stuck | [34 empty] | 11315345840 | 492094529770 | Joseph Westwood Feb 19, 2026 2:56 PM | RC Instructed | KN | Sagging roof felt
28 Aldersey Road Crewe Cheshire | DW_00084_28 |  | CW2 8NR | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/e5ea7d48-17f6-4941-8480-54c368176db6/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 57 | C70 | EWI BATCH |  | Debbie Langer | 2026-03-11 | (V1) IOE/MTP Complete | Planned EWI install |  | 2026-03-12 |  | V1 Uploaded | DMevs, EWI, Loft insulation |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  |  |  | Programmed |  | EWI | Uploaded | 2026-03-27 |  | Archetype (Complex) | [31 empty] | 11302951510 | 473278697709 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed | KN
4 Woodford Close Crewe Cheshire | DW_00092_4 |  | CW2 8QN | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/5fcededb-2d35-4846-aeeb-3dac778a1d5a/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 55 | C71 | EWI BATCH |  | Debbie Langer |  | (V1) IOE/MTP Complete | Planned EWI install EWI would only achieve D58 - Solar would still be need to achieve C. 2.5KW PV modelled. Assessor noted Cavity wall. No boroscope, not convinced. looks like a system build house |  | 2026-03-12 |  | V1 Uploaded | DMevs, Solar PV, EWI |  | V1 Confirmed for invoicing | [9 empty] | EWI | Programmed |  | EWI | Stuck | [34 empty] | 11302951856 | 473599439083 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed | KN
7 Atcherley Close, Nantwich, Cheshire | Remove |  | CW5 8AW |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 66 | [5 empty] | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315325985 | 492032249068 | Joseph Westwood Feb 19, 2026 2:56 PM
51 Wilbraham Road Nantwich Cheshire | Remove |  | CW5 8LQ |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 62 | [5 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302955339 | 473603065077 | Joseph Westwood Feb 18, 2026 12:10 PM
18 Windsor Drive Nantwich Cheshire | Remove |  | CW5 8HZ |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 60 | [5 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302951609 | 473376523503 | Joseph Westwood Feb 18, 2026 12:10 PM
35 Sandfield Avenue, Nantwich, Cheshire | Remove |  | CW5 8EU |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 46 | [5 empty] | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315357700 | 493071408377 | Joseph Westwood Feb 19, 2026 2:56 PM
27 Sandfield, Wrenbury | Remove |  | CW5 8EU |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 41 | [5 empty] | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315340057 | 492016028858 | Joseph Westwood Feb 19, 2026 2:56 PM
9 Council Houses, French Lane End, Nantwich, Cheshire | Remove |  | CW5 8AP |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 33 | [5 empty] | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315357643 | 492012512465 | Joseph Westwood Feb 19, 2026 2:56 PM
24 Peckforton Hall Lane, Tarporley, Cheshire | Remove |  | CW6 9TF |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 23 | [5 empty] | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315340325 | 492949607649 | Joseph Westwood Feb 19, 2026 2:56 PM
4 Sandfield Avenue, Nantwich, Cheshire | Remove |  | CW5 8EP |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 15 | [5 empty] | Ready for Coordination | [21 empty] | Outstanding | [34 empty] | 11315333844 | 492089037024 | Joseph Westwood Feb 19, 2026 2:56 PM
19 Emberton Place Crewe Cheshire | DW_00586_19 |  | CW3 0HL |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302951706 | 473601265904 | Joseph Westwood Feb 18, 2026 12:10 PM
8 Wilbraham Road Nantwich Cheshire | DW_00540_8 |  | CW5 8LQ |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302954927 | 473383802101 | Joseph Westwood Feb 18, 2026 12:10 PM
1 Fittons Close Nantwich Cheshire | DW_00563_1 |  | CW5 8BQ |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302951144 | 473604860106 | Joseph Westwood Feb 18, 2026 12:10 PM
83 Main Road Nantwich Cheshire | DW_00597_83 |  | CW5 7LS |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302951630 | 473686791412 | Joseph Westwood Feb 18, 2026 12:10 PM
34 Broad Lane Nantwich Cheshire | DW_00543_34 |  | CW5 7QL |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302957864 | 473599439084 | Joseph Westwood Feb 18, 2026 12:10 PM
36 Broad Lane Nantwich Cheshire | DW_00543_36 |  | CW5 7QL |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302957549 | 473690409189 | Joseph Westwood Feb 18, 2026 12:10 PM
3 Fittons Close Nantwich Cheshire | DW_00563_3 |  | CW5 8BQ |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302957010 | 473418139894 | Joseph Westwood Feb 18, 2026 12:10 PM
47 Wilbraham Road Nantwich Cheshire | DW_00540_47 |  | CW5 8LQ |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302951628 | 473595810019 | Joseph Westwood Feb 18, 2026 12:10 PM
11 South Croft Tarporley Cheshire | DW_00530_11 |  | CW6 9TQ |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302951705 | 473258805440 | Joseph Westwood Feb 18, 2026 12:10 PM
17 Emberton Place Audlem Crewe | DW_00586_17 |  | CW3 0HL |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302951412 | 473523861723 | Joseph Westwood Feb 18, 2026 12:10 PM
35 Wardle Avenue Nantwich Cheshire | DW_00522_35 |  | CW5 6BQ |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302957521 | 473387396331 | Joseph Westwood Feb 18, 2026 12:10 PM
9 Oakfield Avenue Nantwich Cheshire | DW_00572_9 |  | CW5 8ER |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302951451 | 473690409188 | Joseph Westwood Feb 18, 2026 12:10 PM
30 Sandfield Avenue Nantwich Cheshire | DW_00571_30 |  | CW5 8EU |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302951260 | 473376523504 | Joseph Westwood Feb 18, 2026 12:10 PM
5 Hungerford Place Crewe Cheshire | DW_00553_5 | Shavington | CW2 5PF |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302951350 | 473688591590 | Joseph Westwood Feb 18, 2026 12:10 PM
20 Emberton Place Crewe Cheshire | DW_00586_20 |  | CW3 0HL |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302951289 | 473601228995 | Joseph Westwood Feb 18, 2026 12:10 PM
1 Bunbury Lane Bunbary | DW_00528_1 |  | CW6 9QZ |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302957009 | 473410890989 | Joseph Westwood Feb 18, 2026 12:10 PM
11 Edwards Close Crewe Cheshire | DW_00518_11 | Shavington | CW2 5BU |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302958016 | 473298374856 | Joseph Westwood Feb 18, 2026 12:10 PM
1 Emberton Place Crewe Cheshire | DW_00586_1 |  | CW3 0HL |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302953692 | 473599409378 | Joseph Westwood Feb 18, 2026 12:10 PM
15 Festival Avenue Crewe Cheshire | DW_00588_15 |  | CW3 0DB |  |  |  | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | RA issue | [21 empty] | Outstanding | [34 empty] | 11302957165 | 473610256611 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed
19 Sandfield Wrenbury | DW_00571_19 |  | CW5 8EU |  |  | https://pashub.net/jobs/f4320a02-84d1-431f-bba8-2975ce5dbc02/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | [6 empty] | Outstanding | [21 empty] | Outstanding | [34 empty] | 11302953691 | 473677717723 | Joseph Westwood Feb 18, 2026 12:10 PM
44 Aldersey Road Crewe Cheshire | DW_00084_44 |  | CW2 8NR | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/c696dd3e-32d4-421a-b7a0-3bd02571005a/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 62 | C73 | EWI BATCH | EWI BATCH | Debbie Langer | 2026-02-20 | (V2) IOE/MTP Complete | Planned EWI install, EWI with Dmevs achieves C |  | 2026-03-12 |  | V2 Uploaded | DMevs, EWI |  | V2 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-02-27 |  | Requested |  | H03S400 | Uploaded | 2026-02-27 | A | Archetype (Simple) | Design A completed | [30 empty] | 11302957008 | 473690452175 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed | KN
7 Halton Drive Crewe Cheshire | DW_00107_7 |  | CW2 8TA | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/cea9f84d-0a96-4c92-8627-5fecefd73e23/details | TGP- Atkins | PasHub | Bailey Garner |  | External - Completed | 68 | C75 | Batch 1 | Batch 1 | Debbie Langer | 2026-02-19 | (V1) IOE/MTP Complete | 2KW SE |  | 2026-02-19 |  | V1 Uploaded | DMevs, Loft insulation, Solar PV |  | V1 Confirmed for invoicing | [5 empty] | Luis Arocas Corchero |  |  | 2026-02-27 |  | Programmed |  | H01S903 | Uploaded | 2026-02-27 | A | Repetitive (Simple) | Design A completed | [30 empty] | 11302953942 | 473601228994 | Joseph Westwood Feb 18, 2026 12:10 PM | RC Instructed |  | Roof Felt is coming away- assessor noted roof needs to be looked at before installing Solar.
Test 2 Borden Close |  |  |  | https://www.google.com/ | Yes | https://www.google.com/ |  |  | abdul.koddus@domna.homes | 2026-02-23 | Completed & Uploaded | 63 | C74 | Batch 4 |  | Typhaine Patron | 2026-03-23 | Ready for Coordination | Test RC comments |  |  |  |  | ASHP, DMevs, Ext. doors, Heating controls, HW | [7 empty] | Jun-te Kim |  | 2026-03-24 |  | test design comments | Requested |  | TEST001 | To review |  |  | Archetype (Complex) |  | Approved - others |  | Yes | Test planning comments | N/A | PD render | 3 | Test TB calcs notes | [22 empty] | 11601028424 | 254427203793 | Typhaine Patron Mar 26, 2026 10:53 AM

## filtered
The Guinness Partnership - AtkinsRéalis Coordination & Design Board
Address List (Full PAS)
Name | UPRN | City/Town | Postcode | Sharepoint | Copy Data (tech team) | PasHub Link
115 Underwood Lane | DW_00014_115 |  | CW1 3JP |  |  | https://pashub.net/jobs/23c9089a-23f7-419e-a5f1-bbdc7a6b8980/details
14 Bowen Cooke Avenue | DW_00020_14 |  | CW1 3NR |  |  | https://pashub.net/jobs/587de164-fa6a-4b16-8455-4a226a43641e/details
14 Pear Tree Avenue | DW_00028_14 |  | CW1 3SH |  |  | https://pashub.net/jobs/ef18c670-abb7-45a4-8e40-0ee4c64ea015/details
16 Bowen Cooke Avenue | DW_00020_16 |  | CW1 3NR |  |  | https://pashub.net/jobs/13a51efd-d338-4874-9fd5-1d566a797b11/details
23 Frank Webb Avenue | DW_00019_23 |  | CW1 3NH |  |  | https://pashub.net/jobs/0cd52109-7cff-420a-94e5-b64859eec816/details
33 Bowen Cooke Avenue | DW_00020_33 |  | CW1 3NR |  |  | https://pashub.net/jobs/10de9def-4a6e-4264-9062-7d74afc7938d/details
4 Cartwright Road | DW_00545_4 |  | CW1 5RP |  |  | https://pashub.net/jobs/da531bc6-3290-45af-b39b-6699e741e4c2/details
40 Davenham Crescent | DW_00009_40 |  | CW2 7RZ |  |  | https://pashub.net/jobs/36c84d69-1bf8-4c0f-a439-cf219ce49cf8/details
44 Bowen Cooke Avenue | DW_00020_44 |  | CW1 3NR |  |  | https://pashub.net/jobs/dba849cc-11e6-4ecb-aad1-82ae968fc5f6/details
46 Bowen Cooke Avenue | DW_00020_46 |  | CW1 3NR |  |  | https://pashub.net/jobs/c76a0801-2814-4a64-8997-7b5da8a06e26/details
48 Frank Webb Avenue | DW_00019_48 |  | CW1 3NH |  |  | https://pashub.net/jobs/ad615495-c7ea-46f4-8798-40160cd1cd4b/details
2 Cedar Court Nantwich Cheshire | DW_00513_2 |  | CW5 6RB |  |  | https://pashub.net/jobs/a3566f71-dc74-46a8-ba8c-904ae0ede476/details
12 Queen Street, Tarporley, Cheshire | DW_00529_12 |  | CW6 9QY |  |  | https://pashub.net/jobs/b17afa78-8382-41dd-993e-b95e751460fb/details
161 Cobbs Lane Crewe Cheshire | DW_00558_161 | Shavington | CW2 5JL | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/2d680082-4d1b-4ed9-a6b3-d45a656f3b2c/details
8 St James Close Crewe Cheshire | DW_00611_8 |  | CW3 0BD | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/6937640d-f499-4523-2496-08ddf038716d/details
2 Oakfield Avenue Nantwich Cheshire | DW_00572_2 |  | CW5 8ER | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/db6c3f3b-d739-4726-ab2b-ac9b292c05f1/details
16 Chapel Close, Winsford, Cheshire | DW_00537_16 |  | CW7 4DT |  |  | https://pashub.net/jobs/01d78632-fb87-44f2-aa8c-415f347cbf44/details
5 Queens Crescent, Crewe, Cheshire | DW_00601_5 |  | CW1 4RB |  |  | https://pashub.net/jobs/2918a843-f4e1-442c-af53-1bc6296a961a/details
18 Church Row, Tarporley, Cheshire | DW_00527_18 |  | CW6 9PL |  |  | https://pashub.net/jobs/a117ec8d-a9f8-40d8-9cee-e81585258e7c/details
13 Sandfield Avenue Wrenbury | DW_00571_13 |  | CW5 8EU |  |  | https://pashub.net/jobs/68496525-ddb9-4935-9bb3-3341674b80d1/details
3 Queens Crescent, Crewe, Cheshire | DW_00601_3 |  | CW1 4RB |  |  | https://pashub.net/jobs/37879d0b-db5a-4fef-9013-005703c69016/details
8 East Avenue Crewe Cheshire | DW_00555_8 | Shavington | CW2 5LZ |  |  | https://pashub.net/jobs/02e191a6-a6dc-4d9c-a205-73ca911ea367/details
5 Weaver View Nantwich Cheshire | DW_00599_5 |  | CW5 6EB |  |  | https://pashub.net/jobs/29a4a029-a10f-494b-a42d-299bdbc9ced5/details
4 Festival Avenue Crewe Cheshire | DW_00588_4 |  | CW3 0DB |  |  | https://pashub.net/jobs/93e78bed-02cf-4646-2631-08ddf038716d/details
39 Waterloo Road, Crewe, Cheshire | DW_00551_39 |  | CW1 5TF |  |  | https://pashub.net/jobs/840082ed-53bc-432d-837a-9fbe1de51830/details
2 Tarvin Avenue Crewe Cheshire | DW_00113_2 |  | CW2 8TQ | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/6bba9e13-bc6e-42c8-bce6-8f4594cea9df/details
2 Doddington Road Crewe Cheshire | DW_00077_2 |  | CW2 8ND | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/648db24d-5c80-4a2a-8156-300895bd4fc9/details
23 Doddington Road Crewe Cheshire | DW_00077_23 |  | CW2 8NQ | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/2061f4a6-8f1e-426d-be0d-69f127a1bb72/details
34 Beech Drive Crewe Cheshire | DW_00503_34 |  | CW2 8RE | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/e59e3e3a-f384-4c54-8d3d-271f2faf7f1a/details
36 Albion Street Crewe Cheshire | DW_00040_36 |  | CW2 8NG | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/42a4c6fe-a6b6-4cd9-a9ec-3eb19c145ae7/details
18 Somerford Avenue Crewe Cheshire | DW_00079_18 |  | CW2 8NE | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/eee50ff1-e1af-4187-9e2b-427e5f0b6d57/details
4 Darley Avenue Crewe Cheshire | DW_00080_4 |  | CW2 8NF | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/99e2ce56-4bda-47f0-bdff-7404c6b9e278/details
82 Marshfield Avenue Crewe Cheshire | DW_00111_82 |  | CW2 8TE | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/8564684a-b2af-4406-b205-ce77ce10a62e/details
11 Doddington Road Crewe Cheshire | DW_00077_11 |  | CW2 8ND | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/7d3f0020-ff5b-458f-997c-3db4e1dbc999/details
8 Somerford Avenue Crewe Cheshire | DW_00079_8 |  | CW2 8NE | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/8b3c7834-c207-4203-92e9-506dbf8b81b5/details
43 Albion Street Crewe Cheshire | DW_00040_43 |  | CW2 8NG | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/9c66055f-4a7a-474d-8927-600707540df9/details
2 Gawsworth Avenue Crewe Cheshire | DW_00094_2 |  | CW2 8PB | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/6cb447e9-ad48-49bc-ae6a-0caf81495597/details
5 Darley Avenue Crewe Cheshire | DW_00080_5 |  | CW2 8NF | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/17df2858-f302-413d-b2c4-e442bf7e12c5/details
48 Barthomley Crescent Crewe Cheshire | DW_00110_48 |  | CW2 8TP | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/0b117eac-48f7-4e26-a331-23c8189472dc/details
39 Rockwood Avenue, Crewe, Cheshire, | DW_00006_39 |  | CW2 8LU | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/657ae9ab-e4d8-430d-96da-5c07f8323fd9/details
29 Doddington Road Crewe Cheshire | DW_00077_29 |  | CW2 8NQ | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/4457314a-8c05-4167-a5ce-ccd65c924704/details
24 Rudheath Close Crewe Cheshire | DW_00106_24 |  | CW2 8TL | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/f27d81d2-75ad-4024-899a-c69fce042656/details
20 Alvaston Walk Crewe Cheshire | DW_00097_20 |  | CW2 8PZ | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/2d2addf5-ab27-452e-a2b3-2c87cdf60416/details
2 Somerford Avenue Crewe Cheshire | DW_00079_2 |  | CW2 8NE | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/64e62257-9092-4901-87b7-a01ac729b601/details
79 Marshfield Avenue Crewe Cheshire | DW_00111_79 |  | CW2 8TE | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/068e954a-1a6d-49b1-81e9-8fa689910a0c/details
7 Darley Avenue Crewe Cheshire | DW_00080_7 |  | CW2 8NF | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/2782c0ab-60a3-4d05-8ffe-32f6fbf48119/details
3 Mulberry Road Crewe Cheshire | DW_00607_3 |  | CW2 8UW | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/bac3312d-43cd-4ea8-7f41-08ddf03e139d/details
20 Somerford Avenue Crewe Cheshire | DW_00079_20 |  | CW2 8NE | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/80d2e19a-8371-490c-8a6a-b8676e9c49a6/details
40 Albion Street Crewe Cheshire | DW_00040_40 |  | CW2 8NG | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/f0ac92bf-a9e4-4d1f-a90d-8341541f7bb2/details
5 Alvaston Walk Crewe Cheshire | DW_00097_5 |  | CW2 8PY | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/92d4d67e-8669-416d-8203-533b71c0456e/details
70 Beech Drive Crewe Cheshire | DW_00503_70 |  | CW2 8RQ | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/452d9679-0ade-42c2-93ea-a26b5fc681b5/details
74 Beech Drive Crewe Cheshire | DW_00503_74 |  | CW2 8RQ | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/f1877a10-1f88-4fca-8d3f-195dcd7117e7/details
3 Halton Drive Crewe Cheshire | DW_00107_3 |  | CW2 8TA | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/421642ca-9b0d-4e7a-98d4-b09b06d97a82/details
35 Marshfield Avenue, Crewe, Cheshire | DW_00111_35 |  | CW2 8TH |  |  | https://pashub.net/jobs/43e13a12-8c06-40ce-abd2-f6703260d936/details
12 Oakfield Close Nantwich Cheshire | DW_00573_12 |  | CW5 8ET | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/be5ecdb0-0365-4ec2-a008-546fabbad3a0/details
18 Arnold Street Nantwich Cheshire | DW_00499_18 |  | CW5 5QB | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/fd81c4f0-b130-4ddd-7ff2-08ddf03e139d/details
85 Claughton Avenue Crewe Cheshire | DW_00002_85 |  | CW2 6EY | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/0c1d2d24-61bf-47e9-bbe3-dea8dfbf6308/details
62 Weaver Road, Nantwich, Cheshire, | DW_00403_62 |  | CW5 5NP | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/af5cf08f-3df1-4883-0085-08ddf03803e1/details
11 Volunteer Fields, Nantwich, Cheshire, | DW_00422_11 |  | CW5 5PP | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/3bf88351-63cd-4480-2510-08ddf038716d/details
2 South Croft Tarporley Cheshire | DW_00530_2 |  | CW6 9TQ | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/84ba0b33-50f6-4db7-a2de-261b1f36c042/details
44 Claughton Avenue Crewe Cheshire | DW_00002_44 |  | CW2 6EZ | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/881edff8-173d-4cc7-8851-022a8469dec8/details
17 East Avenue Crewe Cheshire | DW_00555_17 | Shavington | CW2 5LZ | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/a615679b-fce9-41a4-9a6d-e0a86e1e2a0b/details
6 Gorsey Bank Crescent Nantwich Cheshire | DW_00596_6 |  | CW5 7LX | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/c6c012eb-d442-4f5f-83c7-3502cd485da1/details
131 Claughton Avenue Crewe Cheshire | DW_00002_131 |  | CW2 6ET | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/a2314e1f-d83d-4a4e-a4f3-85760d9c0a7a/details
5 Santune Court Rope Lane Crewe Cheshire | DW_00613_5 | Shavington | CW2 5DR | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/68057efa-7d1f-4207-8fa6-4556ed277597/details
142 Claughton Avenue Crewe Cheshire | DW_00002_142 |  | CW2 6EY | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/05cb0c24-818d-4987-a589-d5f47ef1c0b8/details
121 Claughton Avenue Crewe Cheshire | DW_00002_121 |  | CW2 6ET | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/fa47137c-b338-4c34-b37e-a58eb78aebad/details
89 Marsh Lane Nantwich Cheshire | DW_00430_89 |  | CW5 5LD | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/e60e053a-1dc7-48f8-7ff4-08ddf03e139d/details
57 Main Road Nantwich Cheshire | DW_00598_57 |  | CW5 6DN | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/76a1de82-f0bc-42f8-b1b7-1526ee7ae6aa/details
134 Claughton Avenue Crewe Cheshire | DW_00002_134 |  | CW2 6EY | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/86c1670a-8994-4df5-8252-8c7b28e07474/details
24 East Avenue Crewe Cheshire | DW_00555_24 | Shavington | CW2 5LZ | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/6d9aa161-a4e7-4bda-87a8-1b243a905af5/details
57 Barons Road, Shavington, Crewe, Cheshire, | DW_00521_57 | Shavington | CW2 5ER | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/f7fbef8e-8e6c-4e36-9304-d992745e8595/details
127 Claughton Avenue Crewe Cheshire | DW_00002_127 |  | CW2 6ET | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/cf13b2db-86f2-4c3b-ad0f-b1ec43f9ac9e/details
13 Circle Avenue Nantwich Cheshire | DW_00510_13 |  | CW5 7HX | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/c9642c4f-ebb9-4ab9-8355-624c837ec5b8/details
10 Gorsey Bank Crescent Nantwich Cheshire | DW_00596_10 |  | CW5 7LX | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/6833e828-dd12-4f3c-8974-5f87e15f9186/details
100 Main Road Crewe Cheshire | DW_00519_102 | Shavington | CW2 5DU | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/fb6aece3-b0a0-4843-b7f4-9ad98aa25e4e/details
7 Willow Crescent Crewe Cheshire | DW_00505_7 |  | CW2 8RL | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/a7e83906-83c7-494b-b974-89f21812e70b/details
7 School Lane Nantwich Cheshire | DW_00404_7 |  | CW5 5NQ | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/3e004cc9-a912-4c19-7ff1-08ddf03e139d/details
45 Albion Street Crewe Cheshire | DW_00040_45 |  | CW2 8NG | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/b07b33e1-12ad-46da-a61f-956dd2659ed7/details
102 Main Road Crewe Cheshire | DW_00519_100 | Shavington | CW2 5DU | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/0cbfb15c-888e-42cd-959b-032cf1ba0a72/details
20 Acton Road Crewe Cheshire | DW_00105_20 |  | CW2 8TN | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/ffba624d-6941-4559-a48f-bd65009a514e/details
18 Doddington Road Crewe Cheshire | DW_00077_18 |  | CW2 8ND | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/17d19a44-0b86-409a-9089-6ab2dbe455a6/details
7 Stanthorne Avenue Crewe Cheshire | DW_00078_7 |  | CW2 8NH | Batch 2 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%202%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/9ae05e96-3bc0-4e85-aac3-0c1b22677ede/details
6 Circle Avenue, Nantwich, Cheshire | DW_00510_6 |  | CW5 7HX |  |  | https://pashub.net/jobs/a36f5af0-61ad-4dcc-8b38-542bd6a62a7a/details
4 Stanthorne Avenue, Crewe, Cheshire | DW_00078_4 |  | CW2 8NH | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/b0ba13a5-4d5a-4c49-9a18-a108f5af90e2/details
270 Badger Avenue, Crewe, Cheshire | DW_00018_270 |  | CW1 3LW | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/8cbcb830-b036-4e7a-7ff0-08ddf03e139d/details
126 Claughton Avenue, Crewe, Cheshire | DW_00002_126 |  | CW2 6EY | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/3cf4a39e-1142-4d64-81ab-583bd9cc4337/details
7 Dane Place, Crewe, Cheshire | DW_00256_7 |  | CW1 4SA | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/d52fed36-aac0-4ffc-b3a1-c5cca90509c5/details
15 Dane Place, Crewe, Cheshire | DW_00256_15 |  | CW1 4SA | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/fe2b4677-dd48-4406-8d98-07778d46cade/details
47 Rockwood Avenue, Crewe, Cheshire | DW_00006_47 |  | CW2 8LU | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/c54c548c-2bc1-4204-9726-bb73c36c5c17/details
5 Skylark Close, Crewe, Cheshire | DW_00277_5 |  | CW1 3WE | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/65a2ed13-ed53-43d2-8036-08ddf03e139d/details
8 Hazel Grove, Crewe, Cheshire | DW_00181_8 |  | CW1 4JL | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/4ff4d5a4-4cdf-4b1c-9690-35f101c3f38a/details
14 Dane Place, Crewe, Cheshire | DW_00256_14 |  | CW1 4SA | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/5f8cb8d4-c5d6-4624-b104-dcd87dd5139b/details
2 Hurst Court, Tarporley, Cheshire | DW_00612_2 |  | CW6 9QX | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/eb3e7e4b-3bdb-43dd-8ba0-d8b706681242/details
5 Whitlow Avenue, Nantwich, Cheshire | DW_00420_5 |  | CW5 7BN | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/9f9e6a93-4e24-4f90-bf14-21b0d28e213f/details
59 Barons Road Crewe Cheshire | DW_00521_59 | Shavington | CW2 5ER | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/2f24a8ac-3d79-45b4-8566-59b5c05d40ef/details
7 Doddington Road Crewe Cheshire | DW_00077_7 |  | CW2 8ND | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/f3038d42-8f4b-45ba-b8c6-356ffb853f2a/details
21 Coppice Road Nantwich Cheshire | DW_00514_21 |  | CW5 6QA | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/35bcb2fe-a57d-4f68-835e-8c99b1021345/details
2 Weaver View Nantwich Cheshire | DW_00599_2 |  | CW5 6EB | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/1a02fb0e-44d5-4a67-a72c-3ad8900f80b2/details
16 Alvaston Walk Crewe Cheshire | DW_00097_16 |  | CW2 8PZ | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/eb651ec2-c1ce-44bb-bd73-621064557e00/details
43 Wistaston Green Road Crewe Cheshire | DW_00502_43 |  | CW2 8QX | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/21139721-1e4f-4288-9ab8-57d48e92d41f/details
38 Green Lane Nantwich Cheshire | DW_00511_38 |  | CW5 7JB | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/f622458c-3818-4952-9202-1e3ffec916b8/details
14 Tabley Road Crewe Cheshire | DW_00102_14 |  | CW2 8PW | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/5a4004bc-e316-478e-8d05-28a6a51df0c5/details
12 Atcherley Close Nantwich Cheshire | DW_00565_12 |  | CW5 8AW | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/7057f88f-458d-4fb7-8774-80d2cd7a1216/details
7 Festival Avenue Crewe Cheshire | DW_00588_7 |  | CW3 0DB | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/a6107fb0-45b2-4d10-747c-08ddf03a1f35/details
33 Cronkinson Avenue Nantwich Cheshire | DW_00424_33 |  | CW5 7BP | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/a6e75411-a393-4321-9c06-37b8742b4aa2/details
2 Weaver Road Nantwich Cheshire | DW_00403_2 |  | CW5 5NJ | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/629c0496-07b6-4847-a2df-08ddffed72a4/details
6 Mere Close, Crewe, Cheshire | DW_00550_6 |  | CW1 5PR | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/029a2cbe-4539-40aa-869c-6a1a17e5bf25/details
3 Mere Close, Crewe, Cheshire | DW_00550_3 |  | CW1 5PR | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/1f9cc11e-08b4-4a95-893b-d4e55ee2127a/details
49 Plane Tree Drive, Crewe, Cheshire | DW_00068_49 |  | CW1 4ET | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/5aff2995-8dc6-4fd5-83a8-7e89d24314dd/details
5 Crosslands, Crewe, Cheshire | DW_00552_5 |  | CW1 5TG | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/88a93145-582f-4f83-9e65-acc084399994/details
40 Abbey Place, Crewe, Cheshire | DW_00251_40 |  | CW1 4JR | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/a3c4ffff-63b1-4c88-9d6f-641f97099f34/details
13 Dane Place, Crewe, Cheshire | DW_00256_13 |  | CW1 4SA | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/03e0950f-d890-44bc-b2c8-f409b9785075/details
34 Acton Road, Crewe, Cheshire | DW_00105_34 |  | CW2 8TN | Batch 3 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%203%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/1656005e-69e5-4993-b676-7b22b64e8301/details
29 Greenacres, Crewe, Cheshire | DW_00255_29 |  | CW1 4JU | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/d54378b2-1f21-4b50-975f-c56c4bdfc2e6/details
50 Greenacres, Crewe, Cheshire | DW_00255_50 |  | CW1 4JU | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/51f3820f-ba71-4945-83c0-e5d770c09403/details
155 Remer Street, Crewe, Cheshire | DW_00066_155 |  | CW1 4LZ | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/1c06198e-d9a0-405a-8293-a098e65c6dcc/details
10 Henry Street, Crewe, Cheshire | DW_00238_10 |  | CW1 4BH | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/9f11e66e-39f0-4f06-266f-08ddf038716d/details
153 Remer Street, Crewe, Cheshire | DW_00066_153 |  | CW1 4LZ | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/b99380ed-9798-4c3a-9eec-25b273411b6f/details
8 Volunteer Avenue, Nantwich, Cheshire | DW_00417_8 |  | CW5 5PR | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/c25ae43f-d0d0-46f0-2511-08ddf038716d/details
5 Mere Close, Crewe, Cheshire | DW_00550_5 |  | CW1 5PR | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/4c84f9b9-6248-4a6d-bc1d-703e14a56f28/details
107 Claughton Avenue, Crewe, Cheshire | DW_00002_107 |  | CW2 6ET | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/bcab4209-69f8-483b-9978-18d30dc5e5bf/details
41 Wistaston Green Road, Crewe, Cheshire | DW_00502_41 |  | CW2 8QX | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/f24d019c-9e69-4891-99fb-5bfa44bce049/details
21 Edwards Avenue Crewe Cheshire | DW_00517_21 | Shavington | CW2 5BT | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/e29b2917-29a0-48a0-800c-3934a4267401/details
9 Crosslands, Haslington | DW_00552_9 |  | CW1 5TG | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/5848e31a-f0eb-46e4-9dde-e06ce873e8f9/details
144 Lime Tree Avenue, Crewe, Cheshire | DW_00055_144 |  | CW1 4HY | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/3ad81ac6-d904-422e-bb9a-27743a08c739/details
9 Mere Close, Crewe, Cheshire | DW_00550_9 |  | CW1 5PR | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/dda3caa1-cf09-4294-81de-1926f76afd15/details
44 Barthomley Crescent, Crewe, Cheshire | DW_00110_44 |  | CW2 8TP | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/0db50760-4df8-4437-9642-b4802ab1464f/details
18 Oakfield Close, Wrenbury | DW_00573_18 |  | CW5 8ET | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/ff6bf5ac-d5fe-4b13-a705-45573735c20e/details
77A Crewe Road, Crewe, Cheshire | DW_00547_77A |  | CW1 5QX | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/9255a784-a5fb-44cc-8f6b-ebdb2f6b1ebb/details
3 Roedean Walk, Crewe, Cheshire | DW_00253_3 |  | CW1 4LG | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/a7e9f52b-f87f-4705-8152-dbe153d0cf3d/details
14 Somerford Avenue Crewe Cheshire | DW_00079_14 |  | CW2 8NE | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/f5b20f77-dbdc-45fc-bc88-a7c063d4d167/details
167 Remer Street, Crewe, Cheshire | DW_00066_167 |  | CW1 4LZ | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/e09137e0-0d1a-4f37-ae3e-e6aae2188630/details
17 Sherborne Road, Crewe, Cheshire | DW_00250_17 |  | CW1 4LA | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/c2835ab9-2c39-40f7-a0a1-2c18e1e925c8/details
67 Coronation Street, Crewe, Cheshire | DW_00075_67 |  | CW1 4EE | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/1433a2f4-ff3d-4bd4-266e-08ddf038716d/details
10 Darley Avenue Crewe Cheshire | DW_00080_10 |  | CW2 8NF | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/59f0cae5-d1bd-4db2-9411-93c4fd925c45/details
193 Lime Tree Avenue, Crewe, Cheshire | DW_00055_193 |  | CW1 4HZ | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/df71cf83-fb45-481f-9bc0-b58fb51c645d/details
1 St Marys Road, Nantwich, Cheshire | DW_00407_1 |  | CW5 5NU | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/2cdaaca5-571e-48a7-0087-08ddf03803e1/details
32 Marple Crescent Crewe Cheshire | DW_00101_32 |  | CW2 8PP | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/69a107c5-1792-4b55-96b8-ab756970af12/details
34 Doddington Road Crewe Cheshire | DW_00077_34 |  | CW2 8NQ | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/40071b2d-5f41-4db4-af88-b5d9cca1d60b/details
6 White Avenue, Crewe, Cheshire | DW_00013_6 |  | CW2 7SH | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/ea60a30e-37b1-431d-a7ff-e2c13e58f196/details
22 Tabley Road Crewe Cheshire | DW_00102_22 |  | CW2 8PW | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/46f65966-0519-4766-ae99-6026c6121677/details
36 Barons Road Crewe Cheshire | DW_00521_36 | Shavington | CW2 5ER | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/761defaa-e412-4227-8941-6a315566139c/details
4 Chorley Green Nantwich Cheshire | DW_00535_4 |  | CW5 8JR | Batch 4 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%204%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2&newTargetListUrl=%2Fsites%2FSocialHousing%2FShared%20Documents&viewpath=%2Fsites%2FSocialHousing%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | https://pashub.net/jobs/7e3172cf-f737-479b-848b-8efc65832c69/details
23 Cronkinson Avenue Nantwich Cheshire | DW_00424_23 |  | CW5 7BP |  |  | https://pashub.net/jobs/82c0e1e0-93f4-4d4e-b4e6-d41a5330b437/details
25 Marple Crescent Crewe Cheshire | DW_00101_25 |  | CW2 8PP |  |  | https://pashub.net/jobs/3277b32c-fb48-404a-8e71-0192530c4e6d/details
24 Cronkinson Avenue Nantwich Cheshire | DW_00424_24 |  | CW5 7BP |  |  | https://pashub.net/jobs/83e7be10-da07-432f-9163-363b001f4e9d/details
18 Hillfield Gardens Nantwich Cheshire | DW_00411_18 |  | CW5 7BU |  |  | https://pashub.net/jobs/0a734fdc-736d-4b18-a35c-55b78a4a3418/details
113 Marshfield Avenue Crewe Cheshire | DW_00111_113 |  | CW2 8TE |  |  | https://pashub.net/jobs/2b959a8c-51e5-40d8-9dd3-53beff44aeba/details
287 Cobbs Lane Nantwich Cheshire | DW_00558_287 |  | CW5 7NT |  |  | https://pashub.net/jobs/243bdb1d-8778-4d56-81af-330421767a55/details
10 Doddington Road Crewe Cheshire | DW_00077_10 |  | CW2 8ND |  |  | https://pashub.net/jobs/44683795-adce-41c0-9c66-a4b2d9036878/details
213 Lime Tree Avenue, Crewe, Cheshire | DW_00055_213 |  | CW1 4HZ |  |  | https://pashub.net/jobs/61eb8f5c-fd81-4390-b1d4-67bbaa5cf52b/details
12 Stanthorne Avenue Crewe Cheshire | DW_00078_12 |  | CW2 8NH |  |  | https://pashub.net/jobs/d963bc60-13e1-49e1-95c9-a7f5c0ef0fa9/details
6 Atcherley Close, Nantwich, Cheshire | DW_00565_6 |  | CW5 8AW |  |  | https://pashub.net/jobs/4f53a26e-c0fb-460a-8824-50767c3f6965/details
14 Stanthorne Avenue, Crewe, Cheshire | DW_00078_14 |  | CW2 8NH |  |  | https://pashub.net/jobs/b2a1749f-6167-427c-a93e-bc02fc218a0a/details
14 Weaver View Nantwich Cheshire | DW_00599_14 |  | CW5 6EB |  |  | https://pashub.net/jobs/bd29ce85-2815-41f1-9442-e922da6bed67/details
40 Doddington Road, Crewe, Cheshire | DW_00077_40 |  | CW2 8NQ |  |  | https://pashub.net/jobs/ab83bb5e-a873-4177-9743-cfe5bc0a383d/details
45 Wilbraham Road Nantwich Cheshire | DW_00540_45 |  | CW5 8LQ |  |  | https://pashub.net/jobs/d77cd328-1cdb-4d89-935d-e6f915786144/details
13 Stanthorne Avenue Crewe Cheshire | DW_00078_13 |  | CW2 8NH |  |  | https://pashub.net/jobs/3d775072-e8d0-4805-80bb-3e5221d7f89b/details
1 Lightwood Green Avenue Crewe Cheshire | DW_00580_1 |  | CW3 0EN |  |  | https://pashub.net/jobs/0527bab3-46c0-44df-74fd-08ddf03a1f35/details
1 Atcherley Close Nantwich Cheshire | DW_00565_1 |  | CW5 8AW |  |  | https://pashub.net/jobs/06ef13d2-0797-471c-9bf1-98e02d77797b/details
22 Alvaston Walk Crewe Cheshire | DW_00097_22 |  | CW2 8PZ |  |  | https://pashub.net/jobs/44683795-adce-41c0-9c66-a4b2d9036878/details
47 Albion Street Crewe Cheshire | DW_00040_47 |  | CW2 8NG |  |  | https://pashub.net/jobs/c06eab0e-92ec-4e8e-9174-42e0742cdff3/details
1 Oakfield Close, Nantwich, Cheshire | DW_00573_1 |  | CW5 8ET |  |  | https://pashub.net/jobs/1e74c982-f08d-4160-b730-d11754d3ed85/details
27 Wilbraham Road, Nantwich, Cheshire | DW_00540_27 |  | CW5 8LQ |  |  | https://pashub.net/jobs/dc5eb7eb-5410-48eb-9ab0-3367d065e2ed/details
3 Mill Pool Cottages Mill Pool Lane Nantwich | DW_00542_3 |  | CW5 6AU |  |  | https://pashub.net/jobs/16c37b11-2681-43a7-7eea-08ddf03e139d/details
49 Wistaston Green Road Crewe Cheshire | DW_00502_49 |  | CW2 8QX |  |  | https://pashub.net/jobs/0de01973-aee7-4d0d-a15b-e754ac277f04/details
33 Wilbraham Road, Nantwich, Cheshire | DW_00540_33 |  | CW5 8LQ |  |  | https://pashub.net/jobs/eb9cc200-d67a-4038-a84f-e4e2a6d65860/details
1 Crowton Cottages, Winsford, Road, Winsford, Cheshire | DW_00536_1 |  | CW7 4DP |  |  | https://pashub.net/jobs/271f43c3-7246-41df-ae65-ade8bc2bd777/details
3 Sherborne Road, Crewe, Cheshire | DW_00250_3 |  | CW1 4LA |  |  | https://pashub.net/jobs/190f9673-600c-4303-b319-f154f472b33e/details
15 Edwards Close Crewe Cheshire | DW_00518_15 | Shavington | CW2 5BU |  |  | https://pashub.net/jobs/b743f3d9-251a-477d-9042-f509444c2773/details
5 Festival Avenue Crewe Cheshire | DW_00588_5 |  | CW3 0DB |  |  | https://pashub.net/jobs/c1109f01-84e4-4228-7e79-08ddf03e139d/details
18 Chapel Close, Winsford, Cheshire | DW_00537_18 |  | CW7 4DT |  |  | https://pashub.net/jobs/d0bd924d-61a3-411c-8a86-d8c1caee1e04/details
16 Festival Avenue Crewe Cheshire | DW_00588_16 |  | CW3 0DB |  |  | https://pashub.net/jobs/5b58c564-905b-4def-7e76-08ddf03e139d/details
2 Woodford Close Crewe Cheshire | DW_00092_2 |  | CW2 8QN | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/0ff977f5-23c5-4582-8321-a83bae516d8d/details
69 Tatton Road Crewe Cheshire | DW_00090_69 |  | CW2 8PX | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/86ee2faa-dd99-4e1e-8157-5e10237914ff/details
43 Ash Road, Crewe, Cheshire | DW_00058_43 |  | CW1 4DU | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/dae9fe00-b314-4a3d-01e5-08ddf03803e1/details
48 Moreton Road Crewe Cheshire | DW_00085_48 |  | CW2 8QT | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/36c97408-8207-4820-bd91-025c8cd30f5f/details
33 Tatton Road, Crewe, Cheshire | DW_00090_33 |  | CW2 8QA | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/484c9fd3-5462-43bf-a1fe-582aba994818/details
44 Tatton Road, Crewe, Cheshire | DW_00090_44 |  | CW2 8QA | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/d41a77d4-deb3-4980-910f-0c770f10f8d0/details
7 Aldersey Road, Crewe, Cheshire | DW_00084_7 |  | CW2 8NPsl | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/d089cd13-70dd-4392-b4f2-6a0943bdabbd/details
28 Aldersey Road Crewe Cheshire | DW_00084_28 |  | CW2 8NR | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/e5ea7d48-17f6-4941-8480-54c368176db6/details
4 Woodford Close Crewe Cheshire | DW_00092_4 |  | CW2 8QN | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/5fcededb-2d35-4846-aeeb-3dac778a1d5a/details
19 Sandfield Wrenbury | DW_00571_19 |  | CW5 8EU |  |  | https://pashub.net/jobs/f4320a02-84d1-431f-bba8-2975ce5dbc02/details
44 Aldersey Road Crewe Cheshire | DW_00084_44 |  | CW2 8NR | EWI Batch - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FEWI%20Batch%20Assessments%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/c696dd3e-32d4-421a-b7a0-3bd02571005a/details
7 Halton Drive Crewe Cheshire | DW_00107_7 |  | CW2 8TA | Batch 1 - https://domnagroup.sharepoint.com/sites/SocialHousing/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FSocialHousing%2FShared%20Documents%2FOsmosis%2DACD%20Projects%2FAtkins%20Realis%2FThe%20Guinness%20Partnership%2C%20Retrofit%20Assessments%2FBatch%201%20Assessment%20and%20Design&viewid=6ef00ca8%2Dfcc3%2D4b81%2Dacf8%2Df2817e1f08d2 |  | https://pashub.net/jobs/cea9f84d-0a96-4c92-8627-5fecefd73e23/details